## Sheet1
Financial Summary
Date: 2026-11-04
Contract No | Contract Name | Contractor | Contract Amount | Advance Paid (excl.) | Advance Paid (incl.) | Advance Pend (excl.) | Advance Pend (incl. VAT) | IPCs Paid (excl.) | IPCs Paid (incl.) | IPCs Pend (excl.) | IPCs Pend (incl. VAT) | Financial Progress (Mn) | Financial Progress (%) | Fin. Prog. w/ Out. (Mn) | Fin. Prog. w/ Out. (%)
RDA/DRP/SAB/RAT/PEL/19 | Rehabilitation / Improvement and Retaining wall Construction of (Galle - Deniyaya - Madampe Road 144/1 - 144/2 RHS, 135-136/1 LHS & RHS, 137/5-137/4 LHS) & Pelmadulla - Embilipitiya - Nonagama Road 10/4 LHS, 18/1-18/2 LHS) | Solinro Builders | 95082996.58 | 16436817.56 | 19395444.72 | 0 | 0 | 38373715.88 | 45280984.74 | 0 | 0 | 64.6764 | 68% | 64.6764 | 68%
RDA/DRP/NCP/POL/POL/08 | Rehabilitation / Improvement and Reconstruction of 31/1 Culvert, Construction Of Retaining Walls At 31/2 (RHS) on Manampitiya Aralaganwila Maduruoya Road | Sawsiri Construction | 17459311.37 | 0 | 0 | 0 | 0 | 9866233.21 | 11642155.19 | 0 | 0 | 11.6422 | 66.7% | 11.6422 | 66.7%
RDA/DRP/SP/GAL/GAL/02 | Rehabilitation of Gabbion Walls along Galle - Deniyaya - Madampe Road (from7+700-7+730) | Ceylon Construction Industry Development (Pvt) Ltd | 8991852.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%