## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/SAB/RAT/PEL/19 | Rehabilitation / Improvement and Retaining wall Construction of (Galle - Deniyaya - Madampe Road 144/1 - 144/2 RHS, 135-136/1 LHS & RHS, 137/5-137/4 LHS) & Pelmadulla - Embilipitiya - Nonagama Road 10/4 LHS, 18/1-18/2 LHS) | Ratnapura | Ratnapura | Solinro Builders | 100% | 95082996.58 | 105062690.47 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-07 | 2026-07-07
RDA/DRP/NCP/POL/POL/08 | Rehabilitation / Improvement and Reconstruction of 31/1 Culvert, Construction Of Retaining Walls At 31/2 (RHS) on Manampitiya Aralaganwila Maduruoya Road | Polonnaruwa | Polonnaruwa | Sawsiri Construction | 100% | 17459311.37 | 17399611.61 | Awarded | Emergency | Yes | Yes | Yes | 2026-02-06 | 2026-01-09 | 2026-01-09
RDA/DRP/SP/GAL/GAL/02 | Rehabilitation of Gabbion Walls along Galle - Deniyaya - Madampe Road (from7+700-7+730) | Galle | Galle | Ceylon Construction Industry Development (Pvt) Ltd | 100% | 8991852.34 | 10402707.85 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-06 | 2026-09-07