## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/CEN/KDY/KAD/11 | Rehabilitation / Improvement of Nawalapitiya - Dolosbage Road ( B -318) ( 10+500 - 19+350 ), Dedugala Dolosbage Road ( B -588) ( 10+100 - 12+410 ) | Kandy | Kadugannawa | Tiasa Construction (Pvt) Ltd | 26.5% | 193404194.96 | 275515701.42 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-25 | 2026-09-23
RDA/DRP/CEN/KDY/KUN/21 | Improvement of Pitiyegedara-Waththegama-Iriyagasthenna Road (0+000-5+400) | Kandy | Kundasale | Jayasinghe Construction (Pvt) Ltd | 12% | 257721453.96 | 314486807.16 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-30 | 2026-10-28
RDA/DRP/CEN/KDY/KUN/22 | Improvement to Damaged Road Section on Weeragantota - Randenigala Road. (From CH 19+000 To CH 27+200) | Kandy | Kundasale | SD Civil Construction (Pvt) Ltd | 67% | 224968435.78 | 333005906.52 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-25 | 2026-09-23
RDA/DRP/CEN/KDY/KUN/25 | Construction of Gabion Retaining Wall on Katugastota Madawala Bamberella Road(LHS 9+600 - 9+655), (15+450 - 15+500), (10+235 - 10+300) and Wattegama Matale road (0+400 - 0+435) | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 59% | 157909825.01 | 178738774.63 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-06 | 2026-11-01
RDA/DRP/CEN/KDY/KUN/27 | Improvement to Structures on Kandy - Jaffna Road 6+500 - 9+910 | Kandy | Kundasale | Gihan Enterprise | 66% | 113434139.4 | 122896558.88 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-30 | 2026-10-27