## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/CEN/MTL/MTL/32 | Rehabilitation / Improvement of Kandy Jaffna (A-009)(17+710 - 46+450), Thalgodapitiya - Yatawatta - Dombawela (B-409) (15+030 - 26+800), Palapathwela - Galewela Road B-346)(0+000 - 8+100) Roads | Matale | Matale | Lahiru Construction and Consultants (Pvt) Ltd | 68% | 292279354.08 | 395635536.56 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/MTL/MTL/33 | Rehabilitation / Improvement of Wattegama Matale Road (5+280 - 13+160) and Ukuwela Railway station (0+000 - 0+190) | Matale | Matale | Jayasinghe Construction (Pvt) Ltd | 30% | 165006430.79 | 188777407.11 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-07-31
RDA/DRP/CEN/MTL/MTL/35 | Rehabilitation / Improvement of Rattota Gammaduwa Road (7+100 - 11+260) | Matale | Matale | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 63% | 266607902.15 | 291904507.83 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/MTL/NAL/51 | Rehabilitation /Improvement of Retaining wall , drains and shoulder construction Bowathenna Access Road (B-064) (0+000-2+410) | Matale | Nalanda | Platinum Holdings Lanka (Private) Limited | 90% | 17458592.78 | 25992198.15 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-18 | 2026-10-14