## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/CEN/NUE/HAN/57 | Rehabilitation / Improvement of Keerthibandarapura Naranthalawa Road ( B -511 ) ( 0+000 - 4+100 ) | Nuwara Eliya | Hanguranketha | Samindra Construction | 30% | 47755538.96 | 44694533.62 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-30 | 2026-10-28
RDA/DRP/CEN/NUE/NUE/66 | Rehabilitation / Improvement of Nuwara Eliya Town Road (0+000 - 1+695 ) (0+000 - 0+240 ) | Nuwara Eliya | Nuwara Eliya | KSJ Construction (Pvt) Ltd | 69% | 161841095.7 | 205630098.81 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-07-31
RDA/DRP/CEN/NUE/NUE/67 | Rehabilitation / Improvement of Harangala - Kalapitiya - Kumbaloluwa Road (10+480 km - 17+140 km) | Nuwara Eliya | Nuwara Eliya | KSJ Construction (Pvt) Ltd | 78% | 239417811.34 | 302933613.6 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/68 | Rehabilitation / Improvement of Thawalanthenna Thalawakelle Road (0+000 - 8+000) & (10+000 - 33+200) | Nuwara Eliya | Nuwara Eliya | Green Scene Construction (Pvt) Ltd | 40% | 213999600.01 | 296813201.99 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/69 | Rehabilitation / Improvement of Ulapane Pussallawa Road (6+440 - 15+950) | Nuwara Eliya | Nuwara Eliya | Southern Group Civil Construction (Pvt) Ltd | 56% | 266045892.19 | 365868062.33 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/86 | Rehabilitation / Improvement of Approch road to R'way station (Watagoda/ Thalawakele) Road | Nuwara Eliya | Nuwara Eliya | Pragathi Civil Construction | 20% | 33765626.86 | 41996395.31 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-09-10
RDA/DRP/CEN/NUE/NUR/97 | Rehabilitation/Improvement of Nawalapitiya Ginigathena Road (B-319)(7+200-12+200) | Nuwara Eliya | Norwood | Jayawansa Construction (Pvt) Ltd | 62% | 93758217.76 | 104490700.33 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-17 | 2026-09-15