## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/SAB/RAT/PEL/20 | Rehabilitation / Improvement of Pelmadulla - Pelmadulla - Embilipitiya - Nonagama (2+050 - 4+320) & Retaining wall Construction on Pelmadulla - Embilipitiya - Nonagama Road 5/4 - 5/5 (LHS) | Ratnapura | Ratnapura | K.E.P. Construction | 31% | 194327188.51 | 224909805.06 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-06 | 2026-07-06 | 2026-08-06
RDA/DRP/SAB/RAT/EMB/04 | Rehabilitation / Improvement of Galle - Deniyaya-Madampe Road (88+000-95+000) | Ratnapura | Ratnapura | SN Projects Lanka (Pvt) Ltd | 22% | 290799045.34 | 318792416.26 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-07 | 2026-07-07
RDA/DRP/SAB/RAT/EMB/12 | Rehabilitation / Improvement of Galle -Deniyaya-Madampe Road (95+000-100+000) | Ratnapura | Ratnapura | SN Projects Lanka (Pvt) Ltd | 26% | 290733855.4 | 319465519.22 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-07 | 2026-07-07
RDA/DRP/SAB/RAT/RAT/22 | Rehabilitation / Improvement and Asphalt Overlaying on Ayagama Kukulegama Road | Ratnapura | Ratnapura | Keangnam Engineering & Construction (Pvt) Ltd | 42.9% | 280145000.74 | 316600518.19 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-27 | 2026-06-26 | 2026-09-25
RDA/DRP/SAB/RAT/RAT/26 | Rehabilitation / Improvement of Malwala - Carney Road (Ch. 11+000 - Ch. 14+972) | Ratnapura | Ratnapura | SSP Engineers (Pvt) Ltd | 85.8% | 184511228.94 | 199494622.85 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-07 | 2026-07-07 | 2026-07-07
RDA/DRP/SAB/RAT/RAT/25 | Rehabilitation / Improvement and Asphalt Overlaying on Malwana Charney (6+020 - 11+000) & Construction of Gabion Wall at 2+510, 2+847 | Ratnapura | Ratnapura | Wijeratne Construction | 62% | 242356869.5 | 269615801.69 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-07 | 2026-07-07 | 2026-07-07
RDA/DRP/SAB/RAT/PEL/21 | Rehabilitation / Improvement of Pabahinna - Kubalgama - Rajawaka - Kapugala Road (2+000-7+700) & Retaining wall Construction of Colombo - Rathnapura - Wellawaya- Batticaloa Road (156/2 (RHS), 155/6, 133/7 - 133/8 (RHS), 122/5- 122/4 (RHS) | Ratnapura | Ratnapura | Samdam Engineering & Constructions (Pvt) Ltd | 32% | 184536305.86 | 215458780.2 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-06 | 2026-07-06 | 2026-08-06
RDA/DRP/SAB/RAT/RAT/24 | Rehabilitation / Improvement and Asphalt Overlaying on Kalawana - Deepdeen Rakwana (4+255-9+809) | Ratnapura | Ratnapura | SSP Engineers (Pvt) Ltd | 85% | 236752750.59 | 264741911.81 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-07 | 2026-06-24 | 2026-07-07
RDA/DRP/SAB/RAT/EMB/01 | Rehabilitation / Improvement of Kalawana - Deepdeen - Rakwana Road (15+000-46+000) | Ratnapura | Ratnapura | SSP Engineers (Pvt) Ltd | 62% | 287333615.63 | 291908137.8 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-15 | 2026-08-14 | 2026-08-14
RDA/DRP/SAB/RAT/EMB/02 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Nonagama Road (40+500-43+300) | Ratnapura | Ratnapura | Anura Construction | 21% | 260511600.34 | 297894808.58 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-24 | 2026-07-24 | 2026-07-24
RDA/DRP/SAB/RAT/EMB/08 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Naonagama Road (AA018) (43+700-47+000) | Ratnapura | Ratnapura | Anura Construction | 15% | 259436963.35 | 286890596.52 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-10 | 2026-08-09 | 2026-08-09
RDA/DRP/SAB/RAT/EMB/10 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Nonagama Road (AA018) (50+500 - 53+100) & Embilipitiya - Moraketiya - Kiriibbanara - Uda Mauara Road (B549) (0+000-5+500) | Ratnapura | Ratnapura | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 23.7% | 260776583.43 | 271949863.68 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-10 | 2026-08-11
RDA/DRP/SAB/RAT/EMB/05 | Rehabilitation / Improvement of Pelmadulla-Embilipitiya-Nonagama Road (30+000-32+850) | Ratnapura | Ratnapura | Anura Construction | 10% | 248600718.52 | 272308017.25 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-29 | 2026-09-28 | 2026-09-28
RDA/DRP/SAB/RAT/EMB/06 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya-Nonagama Road (33+500-36+500) | Ratnapura | Ratnapura | Anura Construction | 10% | 237998681.32 | 258434888.71 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-29 | 2026-09-28 | 2026-09-28
RDA/DRP/SAB/RAT/EMB/07 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya-Nonagama Road (37+000-40+000) | Ratnapura | Ratnapura | Anura Construction | 15% | 276583785.23 | 299052002.52 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-29 | 2026-09-28 | 2026-09-28
RDA/DRP/SAB/RAT/EMB/09 | Rehabilitation / Improvement of Pelmadulla - Embilipitiya - Naonagama Road (47+100 - 50+400) | Ratnapura | Ratnapura | Anura Construction | 6% | 269913795.48 | 290570516.98 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-09 | 2026-08-28 | 2026-08-28
RDA/DRP/SAB/RAT/EMB/11 | Rehabilitation / Improvement of Weligepola-Hadagiriya - Kapugala (2+000-11+000) | Ratnapura | Ratnapura | D K S Construction | 42% | 273586576.22 | 328908478.03 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-01 | 2026-09-30 | 2026-12-30
RDA/DRP/SAB/RAT/PEL/17 | Rehabilitation / Improvement of Balangoda - Bowatta -Kalthota Road (B038) (24+000-26+000) | Ratnapura | Ratnapura | DKS Nishantha Construction | 60% | 92061086.61 | 101146022.11 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-09-12