## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/EAS/TRI/TRI/06 | Rehabilitation / Improvement of Trincomalee - Pulmoddai Road (47+500 - 49+500) | Trincomalee |  | Southern Group Civil Construction (Pvt) Ltd | 20% | 131314798.09 | 138997580.74 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-06 | 2026-11-02 | 2026-11-02
RDA/DRP/EAS/TRI/TRI/07 | Rehabilitation / Improvement of Retaining Walls of Bridges at Upparu, Ralkuli, and Gangai | Trincomalee |  | Nathans Construction | 82% | 85089780.29 | 99606470.35 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-06 | 2026-11-02 | 2026-11-02
RDA/DRP/EAS/BAT/BAT/01 | Rehabilitation / Improvement and Surfacing from 56+900 km to 58+300km and from 58+640 km to 59+440 km on Bitticaloa - Thurukkondamadu - Trincomalee Road | Batticaloa |  | S S K Construction | 70% | 113074919.76 | 144552679.21 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-25 | 2026-08-24
RDA/DRP/EAS/TRI/TRI/04 | Rehabilitation / Improvement of Town & Gravets Road (B140) (Inner Harbour Road) (0+200 - 0+560) | Trincomalee |  | Motec Engineering & Construction | 65% | 40407339.17 | 45878059.68 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-02 | 2026-08-04
RDA/DRP/EAS/AMP/AMP/01 | Rehabilitation / Improvement of Ampara Uhana Mahoya Road (from 2+400 to 2+800) & (from 3+700 to 3+900), Siyambalanduwa Damana Ampara Road (from 43+000 to 45+000), (from 33+000 to 34+000), (from 35+500 to 36+500) & (from 52+000 to 53+000) and Chadayanthalawa Uhana Road (from 11+100 to 11+500) | Ampara |  | Ediriweera Construction | 90% | 27878955.02 | 31793559.86 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-09-10