## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/CEN/NUE/NUE/60R | Rehabilitation / Improvement of Peradeniya Badulla Chenkaladi Road (A005) (40+750 - 42+850) | Nuwara Eliya | Nuwara Eliya | KSJ Construction (Pvt) Ltd | 10% | 336313078.73 | 338287510.33 | Awarded | Emergency | Yes | Yes | Yes | 2026-10-07 | 2027-04-06
RDA/DRP/CEN/NUE/NUE/66 | Rehabilitation / Improvement of Nuwara Eliya Town Road (0+000 - 1+695 ) (0+000 - 0+240 ) | Nuwara Eliya | Nuwara Eliya | KSJ Construction (Pvt) Ltd | 69% | 161841095.7 | 205630098.81 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-07-31
RDA/DC/DRP/CP/NE/NE/04 | REHABILITAION/ IMPROVEMENTS OF LADY MACALUMS DRIVE ROAD (2+850 - 5+600KM) | Nuwara Eliya | Nuwara Eliya | KDA Weerasinghe & Co (Pvt) Ltd | 1% | 636338397 | 560630000 | Awarded | DC - Roads | Yes | Yes | Yes | 2026-09-17 | 2028-03-15
RDA/DC/DRP/CP/NE/NE/14 | Rehabilitation/ Improvement of Lady Macalums Drive (0+000 - 2+700) | Nuwara Eliya | Nuwara Eliya | K.D.A. Weerasinghe & Co. (Pvt) Ltd | 0% | 711929618.35 | 575100000 | Awarded | DC - Roads
RDA/DC/DRP/CP/NE/NE/05 | Rehabilitation/ Improvement of Blackpool Ambewela Pattipola Hortan Plains (5+200 - 12+000) | Nuwara Eliya | Nuwara Eliya | Asset Engineering (Pvt) Ltd | 0% | 791681996.67 | 612060000 | Awarded | DC - Roads
RDA/DC/DRP/CP/NE/NE/01 | Rehabilitation/ Improvement of Blackpool Ambewela Pattipola Hortan Plains (12+500 - 18+000) | Nuwara Eliya | Nuwara Eliya | Asset Engineering (Pvt) Ltd | 0% | 744680423.8 | 605620000 | Awarded | DC - Roads
RDA/DC/DRP/CP/NE/NE/09 | Rehabilitation/ Improvement to Blackpool Ambewela Pattipola Hortan Plains ( 19+000 - 23+000) | Nuwara Eliya | Nuwara Eliya | Asset Engineering (Pvt) Ltd | 0% | 607139242.74 | 487070000 | Awarded | DC - Roads
RDA/DC/DRP/CP/NE/NE/07 | Rehabilitation/ Improvement to Gomburuoya - Balapokuna Road 0+000-8+500Without 5+250-5+450 & 6+900-7+150 | Nuwara Eliya | Nuwara Eliya | Nagma Engineering (Pvt) Ltd | 0% | 645688890.82 | 521587977.73 | Awarded | DC - Roads
RDA/DC/DRP/SLOPE/CP/NUE/NUE/PACKAGE-31 | REHABILITATION OF SELECTED ROADSECTIONS ON PERADENIYA-BADULLA-CHENKALADI ROAD(44TH KM) AND SLOPE FAILURES DUE TO DITWAH CYCLONE | Nuwara Eliya | Nuwara Eliya | Sanguine Engineering (Pvt) Ltd | 0% | 376649403.13 | 320000000 | Awarded | DC - Slope
RDA/DC/DRP/SLOPE/CP/NUE/NOR/PACKAGE 33 | MITIGATION FOR FAILURE LOCATIONS ALONG NORTON MASKELIYA ROAD (B328) (7+020 7+510) AND SLOPE FAILURES DUE TO "DITWAH" CYCLONE -PACKAGE 33 | Nuwara Eliya | Norwood | HMA Enterprises (Pvt) Ltd | 0% | 220338719.68 | 216000000 | Awarded | DC - Slope