## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/CEN/KDY/KAD/11 | Rehabilitation / Improvement of Nawalapitiya - Dolosbage Road ( B -318) ( 10+500 - 19+350 ), Dedugala Dolosbage Road ( B -588) ( 10+100 - 12+410 ) | Kandy | Kadugannawa | Tiasa Construction (Pvt) Ltd | 26.5% | 193404194.96 | 275515701.42 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-25 | 2026-09-23
RDA/DRP/CEN/KDY/KAN/14 | Rehabilitation /Improvement of Katugasthota Medawala road ( B 0206)( 0 + 000 - 9+370) | Kandy | Kandy | Alucon Industries (Pvt) Ltd | 9% | 74836014.77 | 72827654.9 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-01 | 2027-03-01
RDA/DRP/CEN/KDY/KDY/15 | Rehabilitation / Improvement of Galagedara Rambukkana ( B 122) ( 0+000 - 18+000) | Kandy | Kandy | Jayawansa Construction (Pvt) Ltd | 6% | 79071437.68 | 79953569.86 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-09 | 2027-03-09
RDA/DRP/CEN/KDY/KDY/19 | Rehabilitation / Improvement of Poojapitiya Alawathugoda road ( B 377) ( 0+000 - 8+000) | Kandy | Kandy | Jayawansa Construction (Pvt) Ltd | 5% | 67935586.77 | 64393315.7 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-17 | 2027-03-18
RDA/DRP/CEN/KDY/KUN/20 | Rehabilitation / Improvement to Structures on Madolkelle - Kabaragala - Kandenuwara Road (B 257) (4+000 - 8+000) | Kandy | Kundasale | Samindra Construction | 53% | 31558227.98 | 28660618.7 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-20 | 2026-11-15
RDA/DRP/CEN/KDY/KUN/21 | Improvement of Pitiyegedara-Waththegama-Iriyagasthenna Road (0+000-5+400) | Kandy | Kundasale | Jayasinghe Construction (Pvt) Ltd | 12% | 257721453.96 | 314486807.16 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-30 | 2026-10-28
RDA/DRP/CEN/KDY/KUN/22 | Improvement to Damaged Road Section on Weeragantota - Randenigala Road. (From CH 19+000 To CH 27+200) | Kandy | Kundasale | SD Civil Construction (Pvt) Ltd | 67% | 224968435.78 | 333005906.52 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-25 | 2026-09-23
RDA/DRP/CEN/KDY/KUN/24R | Rehabilitation / Improvement of Flood damage on Katugastota - Madawala - Bamberella Road (B205) (0-000 - 7+200 and 13+000 - 13+045) | Kandy | Kundasale | Nimsara Construction & Engineering (Pvt) Ltd | 5% | 79507501.11 | 80438429.85 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-14 | 2027-03-14
RDA/DRP/CEN/KDY/KUN/25 | Construction of Gabion Retaining Wall on Katugastota Madawala Bamberella Road(LHS 9+600 - 9+655), (15+450 - 15+500), (10+235 - 10+300) and Wattegama Matale road (0+400 - 0+435) | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 59% | 157909825.01 | 178738774.63 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-06 | 2026-11-01
RDA/DRP/CEN/KDY/KUN/26R | Improvement to Structures on Kandy - Jaffna Road 11+700 - 11+850 | Kandy | Kundasale | SD Civil Construction (Pvt) Ltd | 0% | 148430322.65 | 140123428.78 | Awarded | Emergency
RDA/DRP/CEN/KDY/KUN/27 | Improvement to Structures on Kandy - Jaffna Road 6+500 - 9+910 | Kandy | Kundasale | Gihan Enterprise | 66% | 113434139.4 | 122896558.88 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-30 | 2026-10-27
RDA/DRP/CEN/KDY/KUN/29 | Improvement to Structures on Kandy - Mahiyanganaya - Padiyaththalawa Road (24+000-71+500) and Moragahamula victoria damtop | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 61% | 91559621.04 | 100543979.99 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-06 | 2027-01-03
RDA/DRP/CEN/MTL/MTL/31R | Rehabilitation / Improvement of Matale - Udupihilla Road (AB026) (0+000 - 6+000) | Matale | Matale | Alucon Industries (Pvt) Ltd | 7.5% | 63704849.78 | 0 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-01 | 2026-11-30
RDA/DRP/CEN/NUE/NUE/60R | Rehabilitation / Improvement of Peradeniya Badulla Chenkaladi Road (A005) (40+750 - 42+850) | Nuwara Eliya | Nuwara Eliya | KSJ Construction (Pvt) Ltd | 10% | 336313078.73 | 338287510.33 | Awarded | Emergency | Yes | Yes | Yes | 2026-10-07 | 2027-04-06
RDA/DRP/CEN/NUE/NUE/66 | Rehabilitation / Improvement of Nuwara Eliya Town Road (0+000 - 1+695 ) (0+000 - 0+240 ) | Nuwara Eliya | Nuwara Eliya | KSJ Construction (Pvt) Ltd | 69% | 161841095.7 | 205630098.81 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-07-31
RDA/DC/DRP/CP/NE/NE/04 | REHABILITAION/ IMPROVEMENTS OF LADY MACALUMS DRIVE ROAD (2+850 - 5+600KM) | Nuwara Eliya | Nuwara Eliya | KDA Weerasinghe & Co (Pvt) Ltd | 1% | 636338397 | 560630000 | Awarded | DC - Roads | Yes | Yes | Yes | 2026-09-17 | 2028-03-15
RDA/DC/DRP/SLOPE/CP/KDY/GAMPOLA-09 | MITIGATION OF FAILURES ALONG RDA ROADS DUE TO CYCLONE DITWAH GAMPOLA NAWALAPITIYA ROAD (AB013) CHAINAGE 10+350 KM | Kandy | Gampola | Sanguine Engineering (Pvt) Ltd | 9.3% | 386699553.58 | 479898195.86 | Awarded | DC - Slope | Yes | Yes | Yes | 2026-09-03 | 2027-06-30
RDA/DC/DRP/CP/NE/NE/14 | Rehabilitation/ Improvement of Lady Macalums Drive (0+000 - 2+700) | Nuwara Eliya | Nuwara Eliya | K.D.A. Weerasinghe & Co. (Pvt) Ltd | 0% | 711929618.35 | 575100000 | Awarded | DC - Roads
RDA/DC/DRP/CP/NE/NE/05 | Rehabilitation/ Improvement of Blackpool Ambewela Pattipola Hortan Plains (5+200 - 12+000) | Nuwara Eliya | Nuwara Eliya | Asset Engineering (Pvt) Ltd | 0% | 791681996.67 | 612060000 | Awarded | DC - Roads
RDA/DC/DRP/CP/NE/NE/01 | Rehabilitation/ Improvement of Blackpool Ambewela Pattipola Hortan Plains (12+500 - 18+000) | Nuwara Eliya | Nuwara Eliya | Asset Engineering (Pvt) Ltd | 0% | 744680423.8 | 605620000 | Awarded | DC - Roads
RDA/DC/DRP/CP/NE/NE/09 | Rehabilitation/ Improvement to Blackpool Ambewela Pattipola Hortan Plains ( 19+000 - 23+000) | Nuwara Eliya | Nuwara Eliya | Asset Engineering (Pvt) Ltd | 0% | 607139242.74 | 487070000 | Awarded | DC - Roads
RDA/DC/DRP/CP/NE/NE/07 | Rehabilitation/ Improvement to Gomburuoya - Balapokuna Road 0+000-8+500Without 5+250-5+450 & 6+900-7+150 | Nuwara Eliya | Nuwara Eliya | Nagma Engineering (Pvt) Ltd | 0% | 645688890.82 | 521587977.73 | Awarded | DC - Roads
RDA/DC/DRP/SLOPE/CP/MAT/MAT/PACKAGE-23 | REHABILITATION OF SELECTED ROAD SECTIONS ON KALALPITIYA UKUWELA-ELKADUWA ROAD (12th KM) AND SLOPE FAILURES DUE TO DITWAH CYCLONE -PACKAGE -23 | Matale | Matale | Sanguine Engineering (Pvt) Ltd | 0% | 372110778 | 337000000 | Awarded | DC - Slope
RDA/DC/DRP/SLOPE/CP/NUE/NUE/PACKAGE-31 | REHABILITATION OF SELECTED ROADSECTIONS ON PERADENIYA-BADULLA-CHENKALADI ROAD(44TH KM) AND SLOPE FAILURES DUE TO DITWAH CYCLONE | Nuwara Eliya | Nuwara Eliya | Sanguine Engineering (Pvt) Ltd | 0% | 376649403.13 | 320000000 | Awarded | DC - Slope
RDA/DC/DRP/SLOPE/CP/KDY/KUN/PACKAGE 06A | REHABILITATION OF SELECTED ROAD SECTIONS ON KANDY-MAHIYANGANA-PADIYATHALAWA ROAD (34th & 35th KM) & MORAGAHAMULA VICTORIA DAMTOP ROAD (6TH KM) AND SLOPE FAILURES DUE TO "DITWAH" CYCLONE- PACKAGE 06A | Kandy | Kundasale | Finex Engineering (Pvt) Ltd | 0% | 628900686.3 | 614600000 | Awarded | DC - Slope
RDA/DC/DRP/SLOPE/CP/NUE/NOR/PACKAGE 33 | MITIGATION FOR FAILURE LOCATIONS ALONG NORTON MASKELIYA ROAD (B328) (7+020 7+510) AND SLOPE FAILURES DUE TO "DITWAH" CYCLONE -PACKAGE 33 | Nuwara Eliya | Norwood | HMA Enterprises (Pvt) Ltd | 0% | 220338719.68 | 216000000 | Awarded | DC - Slope