## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/CEN/KDY/KDY/19 | Rehabilitation / Improvement of Poojapitiya Alawathugoda road ( B 377) ( 0+000 - 8+000) | Kandy | Kandy | Jayawansa Construction (Pvt) Ltd | 5% | 67935586.77 | 64393315.7 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-17 | 2027-03-18
RDA/DRP/CEN/NUE/NUE/60R | Rehabilitation / Improvement of Peradeniya Badulla Chenkaladi Road (A005) (40+750 - 42+850) | Nuwara Eliya | Nuwara Eliya | KSJ Construction (Pvt) Ltd | 10% | 336313078.73 | 338287510.33 | Awarded | Emergency | Yes | Yes | Yes | 2026-10-07 | 2027-04-06
RDA/DC/DRP/CP/NE/NE/04 | REHABILITAION/ IMPROVEMENTS OF LADY MACALUMS DRIVE ROAD (2+850 - 5+600KM) | Nuwara Eliya | Nuwara Eliya | KDA Weerasinghe & Co (Pvt) Ltd | 1% | 636338397 | 560630000 | Awarded | DC - Roads | Yes | Yes | Yes | 2026-09-17 | 2028-03-15
RDA/DC/DRP/SLOPE/CP/KDY/GAMPOLA-09 | MITIGATION OF FAILURES ALONG RDA ROADS DUE TO CYCLONE DITWAH GAMPOLA NAWALAPITIYA ROAD (AB013) CHAINAGE 10+350 KM | Kandy | Gampola | Sanguine Engineering (Pvt) Ltd | 9.3% | 386699553.58 | 479898195.86 | Awarded | DC - Slope | Yes | Yes | Yes | 2026-09-03 | 2027-06-30