## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/EAS/AKK/AKK/04 | Rehabilitation / Improvement of Newguna – Manikkamadu – Irakkamam Road (0+000-1+250) & (1+300-2+600), Akkaraipattu Degavapi Vangamam Road (8+500-21+500) and Reconstruction of Culvert No. 368/2 on Colombo-Ratnapura-Wellawaya-Batticaloa Road | Ampara |  | Jeezan Trading and Transport | 29% | 171572395.05 | 196038211.02 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-12-10 | 2026-12-10
RDA/DRP/EAS/AKK/KAL/05 | Rehabilitation / Improvement and Reconstruction of Box Culvert at 9+780, Construction of Mass Concrete Retaining Wall (9+550 -9+600) & (9+600-11+000) on Sammanthurai - Malkampiddi - Deegawapi Road, Construction of Concrete Drain & rock blasting with utility shifting on Varaipathanchenai - Deegawapi Road (0+880 - 0+980 RHS), Construction of Concrete Drain on Deegawapi Temple Road (1+100 1+230 RHS), Construction of Mass Concete Retaining wall on Ampilanthurai - Veeramunai Road (25+600 - 26+000 LHS & RHS), Reconstruction of Wing Walls (at 375/2, 375/3, 375/4, 375/6) & Construction of Concrete Drain (384+000-389+000) on Colombo Ratnepura Wellawaya Batticoala Road, Construction of Concrete Drain (15+400 - 15+550 LHS) on Karaitivu - Ampara Road, Construction of Mass Concete Retaining Wall (5+700 -5+730) & on Construction of Hard Shoulder (Concrete) (13+200 - 13+600 LHS & RHS Selected Section) on Weeragoda - Central Camp Road, Construction of Hard Shoulder (Concete) (0+600 - 0+800 LHS & RHS) on Approach Road to Public Buildings | Ampara |  | Nazeeha Hardware and Construction | 23% | 196448155.48 | 236184712.99 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-12-10 | 2026-12-10