## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/WP/GAM/NEG/19 | Rehabilitation / Improvement of Negombo-Mirigama Road (5+000-6+000) and Negombo-Giriulla Road (29+000-34+000) | Gampaha | Gampaha | Tudawe Brothers (Pvt) Ltd | 20% | 206184462.57 | 222010882.78 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-04 | 2026-11-02
RDA/DRP/WP/GAM/NIT/21 | Rehabilitation / Improvement of Hanwella Urapola Road (3+000 - 10+100), Structure Construction on Delgoda Dompe Giridara Road (0+000- 10+070) and Urapola Wathuragama Road (0+000- 7+080 ) and Drain Construction on Negombo-Mirigama road (21+000 - 30+580) | Gampaha | Gampaha | Tudawe Brothers (Pvt) Ltd | 28% | 221768903.84 | 231075356.57 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-04 | 2026-11-02
RDA/DRP/WP/GAM/GAM/10 | Rehabilitation / Improvement of Old Minuwangoda Gampaha - Miriswatta Road (9+000 - 10+000) and Minuwangoda - Gampaha Road (0+000 - 5+300) | Gampaha | Gampaha | Senarath Engineering (Pvt) Ltd | 2% | 92177672.52 | 110481340.2 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-24 | 2026-07-24
RDA/DRP/WP/GAM/GAM/12 | Rehabilitation / Improvement of Acces Road to Peliyagoda interchange (0+000 - 2+100), Colombo - Kandy Road (6+500-19+000) and Kelaniya - Waragoda Road (0+000-3+220) | Gampaha | Gampaha | Senarath Engineering (Pvt) Ltd | 2% | 151956608.92 | 170010323.36 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-24 | 2026-07-24
RDA/DRP/WP/GAM/NIT/20 | Rehabilitation / Improvement of Bothale Mirigama Road (3+750-4+800), Warakapola Kandalama Road (7+000-8+000), (8+500-9+000) & (9+500-10+900), Negombo Mirigama Road and Construction of Gabion Wall on Colombo - Kandy Road at 54+950,Warakapola Kandalama Road at Culvert No. 10/4 LHS and Widening of Culvert Nos. 4/1 LHS 4/3 Bothsides and Reconstruction of Culvert No. 4/2 on Veyangoda Banduragoda Road | Gampaha | Gampaha | Jeyanthan Construction | 46% | 217881464.96 | 245395696.16 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-04 | 2026-09-03
RDA/DRP/WP/GAM/NIT/22 | Rehabilitation / Improvement of Delgoda Dompe Giridara Road (Selected Sections between 2+000-12+100) | Gampaha | Gampaha | Senarath Engineering (Pvt) Ltd | 1% | 264745054.48 | 294920837.23 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-24 | 2026-10-23
RDA/DRP/WP/GAM/NIT/23 | Rehabilitation / Improvement of Kalagedihena Veyangoda Road (0+000 -3+000), Pasyala Attanagalla Road (0+000 - 6+400) and Colombo - Kandy Road (38+620 -38+720) | Gampaha | Gampaha | Senarath Engineering (Pvt) Ltd | 1% | 258218314.97 | 305207472.65 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-24 | 2026-10-23
RDA/DRP/WP/GAM/GAM/13 | Rehabilitation / Improvement and Culvert Constructions on Aluthgama- Vigoda Road at 1+650, on Katunayake - Veyangoda Road at 15+940, on Minuwangoda - Miriswatta - Katana Road at 3+700, on Dunagaha- Nilpanagoda Road at 4+900, on Kadawatha - Mawaramandiya Road at 2+800 and on Makola - Udupila Road at 3+200 | Gampaha | Gampaha | Venus Enterprise | 60% | 34489854.85 | 39535250.16 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-18 | 2026-09-17
RDA/DC/DRP/WP/GAM/NEG/11 | Rehabilitation/ Improvement - Kadawatha - Ragama - Welisara Road (3+000 - 8+050) | Gampaha |  | Komuthi Engineering Services (Pvt) Ltd | 0% | 666616488.15 | 470020000 | Awarded | DC - Roads