## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/CEN/KDY/KAD/11 | Rehabilitation / Improvement of Nawalapitiya - Dolosbage Road ( B -318) ( 10+500 - 19+350 ), Dedugala Dolosbage Road ( B -588) ( 10+100 - 12+410 ) | Kandy | Kadugannawa | Tiasa Construction (Pvt) Ltd | 26.5% | 193404194.96 | 275515701.42 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-25 | 2026-09-23
RDA/DRP/CEN/KDY/KAN/14 | Rehabilitation /Improvement of Katugasthota Medawala road ( B 0206)( 0 + 000 - 9+370) | Kandy | Kandy | Alucon Industries (Pvt) Ltd | 9% | 74836014.77 | 72827654.9 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-01 | 2027-03-01
RDA/DRP/CEN/KDY/KDY/15 | Rehabilitation / Improvement of Galagedara Rambukkana ( B 122) ( 0+000 - 18+000) | Kandy | Kandy | Jayawansa Construction (Pvt) Ltd | 6% | 79071437.68 | 79953569.86 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-09 | 2027-03-09
RDA/DRP/CEN/KDY/KDY/19 | Rehabilitation / Improvement of Poojapitiya Alawathugoda road ( B 377) ( 0+000 - 8+000) | Kandy | Kandy | Jayawansa Construction (Pvt) Ltd | 5% | 67935586.77 | 64393315.7 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-17 | 2027-03-18
RDA/DRP/CEN/KDY/KUN/20 | Rehabilitation / Improvement to Structures on Madolkelle - Kabaragala - Kandenuwara Road (B 257) (4+000 - 8+000) | Kandy | Kundasale | Samindra Construction | 53% | 31558227.98 | 28660618.7 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-20 | 2026-11-15
RDA/DRP/CEN/KDY/KUN/21 | Improvement of Pitiyegedara-Waththegama-Iriyagasthenna Road (0+000-5+400) | Kandy | Kundasale | Jayasinghe Construction (Pvt) Ltd | 12% | 257721453.96 | 314486807.16 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-30 | 2026-10-28
RDA/DRP/CEN/KDY/KUN/22 | Improvement to Damaged Road Section on Weeragantota - Randenigala Road. (From CH 19+000 To CH 27+200) | Kandy | Kundasale | SD Civil Construction (Pvt) Ltd | 67% | 224968435.78 | 333005906.52 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-25 | 2026-09-23
RDA/DRP/CEN/KDY/KUN/24R | Rehabilitation / Improvement of Flood damage on Katugastota - Madawala - Bamberella Road (B205) (0-000 - 7+200 and 13+000 - 13+045) | Kandy | Kundasale | Nimsara Construction & Engineering (Pvt) Ltd | 5% | 79507501.11 | 80438429.85 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-14 | 2027-03-14
RDA/DRP/CEN/KDY/KUN/25 | Construction of Gabion Retaining Wall on Katugastota Madawala Bamberella Road(LHS 9+600 - 9+655), (15+450 - 15+500), (10+235 - 10+300) and Wattegama Matale road (0+400 - 0+435) | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 59% | 157909825.01 | 178738774.63 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-06 | 2026-11-01
RDA/DRP/CEN/KDY/KUN/26R | Improvement to Structures on Kandy - Jaffna Road 11+700 - 11+850 | Kandy | Kundasale | SD Civil Construction (Pvt) Ltd | 0% | 148430322.65 | 140123428.78 | Awarded | Emergency
RDA/DRP/CEN/KDY/KUN/27 | Improvement to Structures on Kandy - Jaffna Road 6+500 - 9+910 | Kandy | Kundasale | Gihan Enterprise | 66% | 113434139.4 | 122896558.88 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-30 | 2026-10-27
RDA/DRP/CEN/KDY/KUN/29 | Improvement to Structures on Kandy - Mahiyanganaya - Padiyaththalawa Road (24+000-71+500) and Moragahamula victoria damtop | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 61% | 91559621.04 | 100543979.99 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-06 | 2027-01-03
RDA/DC/DRP/SLOPE/CP/KDY/GAMPOLA-09 | MITIGATION OF FAILURES ALONG RDA ROADS DUE TO CYCLONE DITWAH GAMPOLA NAWALAPITIYA ROAD (AB013) CHAINAGE 10+350 KM | Kandy | Gampola | Sanguine Engineering (Pvt) Ltd | 9.3% | 386699553.58 | 479898195.86 | Awarded | DC - Slope | Yes | Yes | Yes | 2026-09-03 | 2027-06-30
RDA/DC/DRP/SLOPE/PD(CP)/KDY/GPL/01 | Construction of Slope failure mitigation measures along Peradeniya-Badulla-Chenkaladi Road (A005) at Ch 0+030 km | Kandy | Gampola | Weebadda Construction | 0% | 22481370 | 26379398.72 | Awarded | PD(CP) - Slope
RDA/DC/DRP/SLOPE/PD(CP)/KDY/GPL/11 | Construction of Slope failure mitigation measures along Galaha-Pupuressa-Delpitiya Road (B125) at Ch 5+700 km | Kandy | Gampola | J. Kodithuwakkuarachchi & Sons (Pvt) Ltd | 0% | 17724816 | 16121754.76 | Awarded | PD(CP) - Slope
RDA/DC/DRP/SLOPE/PD(CP)/KDY/GPL/14 | Construction of Slope failure mitigation measures along Atabage-Ulapane Road (B 490) at Ch 4+000 km | Kandy | Gampola | Bandaranayake Builders and Construction | 0% | 24796315.46 | 23436975.14 | Awarded | PD(CP) - Slope
RDA/DC/DRP/SLOPE/PD(CP)/KDY/GPL/29 | Construction of Slope failure mitigation measures along Peradeniya-Badulla-Chenkaladi Road (A005) at Ch 21+550 km | Kandy | Gampola | Weebadda Construction | 0% | 28806688.5 | 34156473.18 | Awarded | PD(CP) - Slope
RDA/DC/DRP/SLOPE/PD(CP)/KDY/KUN/26A | Construction of Slope failure mitigation measures along Kandy-Mahiyangana-Padiyathalawa Road (A026) at Culvert No 58/6 -58/5. | Kandy | Kundasale | J. Kodithuwakkuarachchi & Sons (Pvt) Ltd | 0% | 25255788 | 20549739.77 | Awarded | PD(CP) - Slope | â€” | â€” | â€”
RDA/DC/DRP/SLOPE/PD(CP)/KDY/KUN/18,19&20 | Construction of Slope failure mitigation measures along Kandy – Mahiyangana – Padiyatalawa Road (A026) at Culvert No 47/5 Culvert No47/10, Culvert No 50/6-51+200 km and Culvert No 52/3-Culvert No 52/5 | Kandy | Kundasale | J. Kodithuwakkuarachchi & Sons (Pvt) Ltd | 0% | 19636680 | 16043059.21 | Awarded | PD(CP) - Slope
RDA/DC/DRP/SLOPE/PD(CP)/KDY/KUN/1A | Construction of Slope failure mitigation measures along KandyMahiyanganaPadiyathalawa Road (A026) at Culvert No 25/3. | Kandy | Kundasale | J. Kodithuwakkuarachchi & Sons (Pvt) Ltd | 0% | 12938500 | 16475449.99 | Awarded | PD(CP) - Slope
RDA/DC/DRP/SLOPE/PD(CP)/KDY/KAD/35 | Construction of Slope failure mitigation measures along Aladeniya-Eriyagama Road (B005) at Ch 3+700 RHS. | Kandy | Kadugannawa | Weebadda Construction | 0% | 26072370 | 28669432.07 | Awarded | PD(CP) - Slope
RDA/DC/DRP/SLOPE/CP/KDY/KUN/PACKAGE 06A | REHABILITATION OF SELECTED ROAD SECTIONS ON KANDY-MAHIYANGANA-PADIYATHALAWA ROAD (34th & 35th KM) & MORAGAHAMULA VICTORIA DAMTOP ROAD (6TH KM) AND SLOPE FAILURES DUE TO "DITWAH" CYCLONE- PACKAGE 06A | Kandy | Kundasale | Finex Engineering (Pvt) Ltd | 0% | 628900686.3 | 614600000 | Awarded | DC - Slope
RDA/DC/DRP/SLOPE/CP/KDY/KAD/PACKAGE 14B | MITIGATION FOR FAILURE LOCATIONS ALONG NAWALAPITIYA DOLOSBAGE ROAD (B318) (15+000 - 16+000) DUE TO "DITWAH" CYCLONE - PACKAGE 14B | Kandy | Kadugannawa | HMA Enterprises (Pvt) Ltd | 0% | 139111261.28 | 130000000 | Awarded | DC - Slope