## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/CEN/KDY/KAN/14 | Rehabilitation /Improvement of Katugasthota Medawala road ( B 0206)( 0 + 000 - 9+370) | Kandy | Kandy | Alucon Industries (Pvt) Ltd | 9% | 74836014.77 | 72827654.9 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-01 | 2027-03-01
RDA/DRP/CEN/KDY/KDY/15 | Rehabilitation / Improvement of Galagedara Rambukkana ( B 122) ( 0+000 - 18+000) | Kandy | Kandy | Jayawansa Construction (Pvt) Ltd | 6% | 79071437.68 | 79953569.86 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-09 | 2027-03-09
RDA/DRP/CEN/KDY/KUN/24R | Rehabilitation / Improvement of Flood damage on Katugastota - Madawala - Bamberella Road (B205) (0-000 - 7+200 and 13+000 - 13+045) | Kandy | Kundasale | Nimsara Construction & Engineering (Pvt) Ltd | 5% | 79507501.11 | 80438429.85 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-14 | 2027-03-14
RDA/DRP/CEN/KDY/KUN/29 | Improvement to Structures on Kandy - Mahiyanganaya - Padiyaththalawa Road (24+000-71+500) and Moragahamula victoria damtop | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 61% | 91559621.04 | 100543979.99 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-06 | 2027-01-03