## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/CEN/NUE/HAN/57 | Rehabilitation / Improvement of Keerthibandarapura Naranthalawa Road ( B -511 ) ( 0+000 - 4+100 ) | Nuwara Eliya | Hanguranketha | Samindra Construction | 30% | 47755538.96 | 44694533.62 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-30 | 2026-10-28
RDA/DRP/CEN/NUE/NUE/60R | Rehabilitation / Improvement of Peradeniya Badulla Chenkaladi Road (A005) (40+750 - 42+850) | Nuwara Eliya | Nuwara Eliya | KSJ Construction (Pvt) Ltd | 10% | 336313078.73 | 338287510.33 | Awarded | Emergency | Yes | Yes | Yes | 2026-10-07 | 2027-04-06
RDA/DRP/CEN/NUE/NUE/66 | Rehabilitation / Improvement of Nuwara Eliya Town Road (0+000 - 1+695 ) (0+000 - 0+240 ) | Nuwara Eliya | Nuwara Eliya | KSJ Construction (Pvt) Ltd | 69% | 161841095.7 | 205630098.81 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-07-31
RDA/DRP/CEN/NUE/NUE/67 | Rehabilitation / Improvement of Harangala - Kalapitiya - Kumbaloluwa Road (10+480 km - 17+140 km) | Nuwara Eliya | Nuwara Eliya | KSJ Construction (Pvt) Ltd | 78% | 239417811.34 | 302933613.6 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/68 | Rehabilitation / Improvement of Thawalanthenna Thalawakelle Road (0+000 - 8+000) & (10+000 - 33+200) | Nuwara Eliya | Nuwara Eliya | Green Scene Construction (Pvt) Ltd | 40% | 213999600.01 | 296813201.99 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/69 | Rehabilitation / Improvement of Ulapane Pussallawa Road (6+440 - 15+950) | Nuwara Eliya | Nuwara Eliya | Southern Group Civil Construction (Pvt) Ltd | 56% | 266045892.19 | 365868062.33 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/86 | Rehabilitation / Improvement of Approch road to R'way station (Watagoda/ Thalawakele) Road | Nuwara Eliya | Nuwara Eliya | Pragathi Civil Construction | 20% | 33765626.86 | 41996395.31 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-09-10
RDA/DRP/CEN/NUE/NUR/97 | Rehabilitation/Improvement of Nawalapitiya Ginigathena Road (B-319)(7+200-12+200) | Nuwara Eliya | Norwood | Jayawansa Construction (Pvt) Ltd | 62% | 93758217.76 | 104490700.33 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-17 | 2026-09-15
RDA/DRP/CEN/NUE/NUR/98 | Rehabilitation/Improvement Harangala Kalapitiya Road (B-148) (0+000-10+700), Approach Road to Hrangala Dam Crest Road (B-491) (0+000-3+820), Nawalapitiya Harangala Road (B-306) (0+000-10+700) | Nuwara Eliya | Norwood | Pragathi Civil Construction | 44% | 188617394.68 | 222691835.72 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-18 | 2026-12-16
RDA/DRP/CEN/NUE/NUR/101 | Rehabilitation/Improvement of Hatton Maskeliya Delhouse Road (B-149) (0+000-31+970) | Nuwara Eliya | Norwood | Sooriya Builders | 31% | 86746198.17 | 108611538.67 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-18 | 2026-11-11
RDA/DC/DRP/CP/NE/NRW/02 | REHABILITATION/ IMPROVEMENT OF APPROCH ROAD TO LAXAPANA POWER HOUSE ROAD CH 6+100 - 12+000 | Nuwara Eliya | Norwood | U.K.S Lanka Engineering (Pvt) Ltd | 9% | 374859845.1 | 348620000 | Awarded | DC - Roads | Yes | Yes | Yes | 2026-07-30 | 2027-07-29
RDA/DC/DRP/CP/NE/NE/04 | REHABILITAION/ IMPROVEMENTS OF LADY MACALUMS DRIVE ROAD (2+850 - 5+600KM) | Nuwara Eliya | Nuwara Eliya | KDA Weerasinghe & Co (Pvt) Ltd | 1% | 636338397 | 560630000 | Awarded | DC - Roads | Yes | Yes | Yes | 2026-09-17 | 2028-03-15
RDA/DC/DRP/CP/NE/NRW/03 | REHABILITATION/ IMPROVEMENT TO ROZELLA RAILWAY STATION ROAD (0+000 - 3+300) KM AND WATAWALA RAILWAY STATION ROAD (0+000 - 1+850) KM | Nuwara Eliya | Norwood | Nagma Engineering (Pvt) Ltd | 19% | 604298969.28 | 509310000 | Awarded | DC - Roads | Yes | Yes | Yes | 2026-09-16 | 2027-09-14
RDA/DC/DRP/CP/NE/NE/14 | Rehabilitation/ Improvement of Lady Macalums Drive (0+000 - 2+700) | Nuwara Eliya | Nuwara Eliya | K.D.A. Weerasinghe & Co. (Pvt) Ltd | 0% | 711929618.35 | 575100000 | Awarded | DC - Roads
RDA/DC/DRP/CP/NE/NE/05 | Rehabilitation/ Improvement of Blackpool Ambewela Pattipola Hortan Plains (5+200 - 12+000) | Nuwara Eliya | Nuwara Eliya | Asset Engineering (Pvt) Ltd | 0% | 791681996.67 | 612060000 | Awarded | DC - Roads
RDA/DC/DRP/CP/NE/NE/01 | Rehabilitation/ Improvement of Blackpool Ambewela Pattipola Hortan Plains (12+500 - 18+000) | Nuwara Eliya | Nuwara Eliya | Asset Engineering (Pvt) Ltd | 0% | 744680423.8 | 605620000 | Awarded | DC - Roads
RDA/DC/DRP/CP/NE/NE/09 | Rehabilitation/ Improvement to Blackpool Ambewela Pattipola Hortan Plains ( 19+000 - 23+000) | Nuwara Eliya | Nuwara Eliya | Asset Engineering (Pvt) Ltd | 0% | 607139242.74 | 487070000 | Awarded | DC - Roads
RDA/DC/DRP/CP/NE/NE/07 | Rehabilitation/ Improvement to Gomburuoya - Balapokuna Road 0+000-8+500Without 5+250-5+450 & 6+900-7+150 | Nuwara Eliya | Nuwara Eliya | Nagma Engineering (Pvt) Ltd | 0% | 645688890.82 | 521587977.73 | Awarded | DC - Roads
RDA/DC/DRP/SLOPE/CP/NUE/NUE/PACKAGE-31 | REHABILITATION OF SELECTED ROADSECTIONS ON PERADENIYA-BADULLA-CHENKALADI ROAD(44TH KM) AND SLOPE FAILURES DUE TO DITWAH CYCLONE | Nuwara Eliya | Nuwara Eliya | Sanguine Engineering (Pvt) Ltd | 0% | 376649403.13 | 320000000 | Awarded | DC - Slope
RDA/DC/DRP/SLOPE/CP/NUE/NOR/PACKAGE 33 | MITIGATION FOR FAILURE LOCATIONS ALONG NORTON MASKELIYA ROAD (B328) (7+020 7+510) AND SLOPE FAILURES DUE TO "DITWAH" CYCLONE -PACKAGE 33 | Nuwara Eliya | Norwood | HMA Enterprises (Pvt) Ltd | 0% | 220338719.68 | 216000000 | Awarded | DC - Slope
RDA/DC/DRP/SLOPE/CP/NUE/NUE/PACKAGE-03 | MITIGATION OF SLOPE FAILURE LOCATIONS ALONG GOMBURU OYA-BALAPOKUNA ROAD (B582) 6+900 KM-7+100 KM DUE TO DITWAH CYCLONE - PACKAGE 03 | Nuwara Eliya | Nuwara Eliya | Nagma Engineering (Pvt) Ltd | 0% | 357941434.5 | 262030000 | Awarded | DC - Slope
RDA/DC/DRP/SLOPE/CP/NUE/HAN/PACKAGE 26E | REHABILITATION OF SELECTED ROAD SECTIONS ON THENNEKUMBURA RIKILLAGASKADA RAGALA ROAD (B413) (50+100-70+950 ) AND SLOPE FAILURES DUE TO "DITWAH" CYCLONE-PACKAGE 26E | Nuwara Eliya | Hanguranketha | Nagma Engineering (Pvt) Ltd | 0% | 332123863.5 | 322400000 | Awarded | DC - Slope
RDA/DC/DRP/SLOPE/CP/NUE/HAN/PACKAGE 26C | MITIGATION FOR FAILURE LOCATIONS ALONG THENNEKUMBURA RIKILLAGASKADA RAGALA ROAD (B413) (48/11 - 48/12) & (67/10 - 67 km) DUE TO "DITWAH" CYCLONE-PACKAGE 26C | Nuwara Eliya | Hanguranketha | Finex Engineering (Pvt) Ltd | 0% | 180175018.14 | 159300000 | Awarded | DC - Slope
RDA/DC/DRP/SLOPE/CP/NUE/NOR/PACKAGE 28A | MITIGATION FOR FAILURE LOCATIONS ALONG AWISSAWELLA HATTON NUWARAELIYA ROAD (A007) (41+800 & 42+960) DUE TO "DITWAH" CYCLONE - PACKAGE 28A | Nuwara Eliya | Norwood | Finex Engineering (Pvt) Ltd | 0% | 264416347.31 | 232200000 | Awarded | DC - Slope