## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/NWP/CHI/CHI/08 | Rehabilitation / Improvement of Baththuluoya - Udappuwa - Andimunai Road (B614) at 6+100 in Chilaw EE Division | Puttalam | Chilaw | ST MARY Construction | 56% | 83944711.21 | 84197870.47 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-08-15 | 2026-10-14
RDA/DRP/NWP/CHI/CHI/07 | Rehabilitation / Improvement of Nainamadama – Iranavila - Chilaw Road (B640) (6+200 - 32+200), Bangadeniya - Adigama – Anamaduwa Road (B045) (2+200 - 13+400) and Peliyagoda - Puttala Road (A003) (78+100 - 93+200) in Chilaw EE Division | Puttalam | Chilaw | Jayawansa Construction (Pvt) Ltd | 28% | 214608362.18 | 248319499.59 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-22 | 2027-01-20
RDA/DRP/NWP/CHI/PUT/10 | Rehabilitation / Improvement of Palavi - Kalpitiya Road (B349) and Etalai - Talawila (Jubily Mawatha) Road (B516) (0+900-1+200) Puttalam EE Division | Puttalam | Chilaw | ST MARY Construction | 14% | 136011633.11 | 147930527.03 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-02 | 2026-12-01
RDA/DRP/NWP/CHI/PUT/11 | Rehabilitation / Improvement of Town Roads (Saltern Road, Marikkar Street, Poles Road, Rest House Road, Good Shed Road) and Puttalam Trincomalee Road (AA012) in Puttalam EE Division | Puttalam | Chilaw | Omega Construction Company (Pvt) Ltd | 35% | 303043337.3 | 290051718.48 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-02 | 2026-12-01
RDA/DRP/NWP/CHI/PUT/12 | Rehabilitation / Improvement of Puttalam Marichchikaddi Road in Puttalam 6+100-9+000 | Puttalam | Chilaw | Omega Construction Company (Pvt) Ltd | 26% | 141404654.67 | 143347737.52 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-18 | 2026-12-17