## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DPR/NCP/ANU/ANU/02 | Rehabilitation / Improvement and Construction of Drainge Canal for Kumbichchan Kulama Spillway on Maitreepala Senanayake Mawatha (1+970 - 2+090 km) | Anuradhapura | Anuradhapura | SMA Construction (Pvt) Ltd | 50% | 138891057.65 | 178990814.77 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-20 | 2026-10-19 | 2026-10-19
RDA/DPR/NCP/ANU/ANU/03 | Rehabilitation / Improvement Construction of Drainge Canal for Thambuttegama Tank Spill on Padeniya - Anuradhapura Road (59+420 - 59+610) & Construction of Drainge Canal for Protection Road on Andarawewa - Balaluwewa Road(16+580 - 16+680) | Anuradhapura | Anuradhapura | SMA Construction (Pvt) Ltd | 38% | 132437825.5 | 174596369.9 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-20 | 2026-10-19 | 2026-10-19
RDA/DPR/NCP/ANU/ANU/01 | Rehabilitation / Improvement of Andarawewa - Balaluwewa Road (B501) (21+330 - 21+ 580 km) | Anuradhapura | Anuradhapura | Ranuja Construction | 16% | 99497834.48 | 85106787.1 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-23 | 2026-10-22 | 2027-10-21
RDA/DRP/NCP/ANU/MAR/05R | Rehabilitation / Improvement and Rectification of Flood Damage on Thonigala - Kalawewa - Galewela Road (B423) (14+000-14+085 km) & Rectification of Flood Damage on Madatugama Pubbogama Andiyagala Road (B556) (11+930 -12+250 km) | Anuradhapura | Anuradhapura | NMST Contractors | 12% | 89094024.31 | 93874634.26 | Awarded | Emergency | Yes | Yes | Yes | 2026-08-28 | 2026-11-27
RDA/DRP/NCP/ANU/MED/07 | Rehabilitation / Improvement of Flood Damaged - Shoulder & Embankment Protection for Puttalam - Trincomalee Road (AA012) (131+100-131+400 LHS/RHS) (139+020-139+100 LHS) , Kandy -Jaffna Road (AA009) ( 148+775-149+050) and Kebithigollewa - Padaviya Road (B211) (17+400-17+550) | Anuradhapura | Anuradhapura | The Crown Construction | 47% | 38223285.38 | 45054035.76 | Awarded | Emergency | Yes | Yes | Yes | 2026-02-06 | 2026-01-09 | 2026-01-09