## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/WP/COL/AVI/02 | Rehabilitation / Improvement of Damage Sections on Colombo - Hanwella Low Level Road (AB010) (23+000 - 26+715) & Hanwella Cross Road (B145) (0+000 - 0+800) | Colombo | Colombo | Keangnam Engineering & Construction (Pvt) Ltd | 29% | 279374027.9 | 299392762.2 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-21 | 2026-07-21 | 2026-08-08
RDA/DRP/WP/COL/AVI/03 | Rehabilitation / Improvement and Asphalt Overlaying on Colombo - Horana Road (B084) (10+500 - 13+500) | Colombo | Colombo | Keangnam Engineering & Construction (Pvt) Ltd | 3% | 176739557.41 | 201633881.18 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-21 | 2026-06-23 | 2026-07-11
RDA/DRP/WP/COL/AVI/04 | Rehabilitation / Improvement and Asphalt Overlaying on Mampe Kottawa Road (B267) (0+750 - 3+400) (5+100 - 6+120)) | Colombo | Colombo | Keangnam Engineering & Construction (Pvt) Ltd | 65% | 94697340.01 | 108030624.38 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-21 | 2026-06-23 | 2026-07-11
RDA/DRP/WP/COL/AVI/05 | Rehabilitation / Improvement and Asphalt Overlaying on Panagoda Henpita Road (B354) (0+000 - 6+440) | Colombo | Colombo | Keangnam Engineering & Construction (Pvt) Ltd | 3% | 225228168.18 | 250078803.62 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-21 | 2026-06-23 | 2026-07-11
RDA/DRP/WP/COL/COL/06 | Rehabilitation / Improvement of Allen Avenue (B011) (0+000- 2+000) | Colombo | Colombo | Jayasinghe Construction (Pvt) Ltd | 5% | 144822585.09 | 146669652.6 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-10 | 2026-08-09
RDA/DRP/WP/COL/COL/09 | Rehabilitation / Improvement of Koralawella Egodauyana Road (B235) section 2 (3+000 - 6+300) | Colombo | Colombo | Jayasinghe Construction (Pvt) Ltd | 5% | 155082468.4 | 160664947.64 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-10 | 2026-08-09
RDA/DRP/WP/COL/AVI/01 | Rehabilitation / Improvement and Drain and Shoulder Construction at Locations Within 38+200 - 60+950 on Colombo - Ratnapura - Wellawaya - Batticaloa Road (AA004) | Colombo | Colombo | Greenwawe Construction (Pvt) Ltd | 26% | 210347639.08 | 239974678.56 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-10 | 2026-07-12 | 2026-07-23
RDA/DRP/WP/COL/COL/07 | Rehabilitation / Improvement of Colombo Hanwella Road (0+370 - 20+400) | Colombo | Colombo | INK Engineering | 12% | 146665907.47 | 140313104.48 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-25 | 2026-08-24 | 2026-08-24