## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/CEN/KDY/KAN/14 | Rehabilitation /Improvement of Katugasthota Medawala road ( B 0206)( 0 + 000 - 9+370) | Kandy | Kandy | Alucon Industries (Pvt) Ltd | 9% | 74836014.77 | 72827654.9 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-01 | 2027-03-01
RDA/DRP/CEN/KDY/KDY/15 | Rehabilitation / Improvement of Galagedara Rambukkana ( B 122) ( 0+000 - 18+000) | Kandy | Kandy | Jayawansa Construction (Pvt) Ltd | 6% | 79071437.68 | 79953569.86 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-09 | 2027-03-09
RDA/DRP/CEN/KDY/KDY/19 | Rehabilitation / Improvement of Poojapitiya Alawathugoda road ( B 377) ( 0+000 - 8+000) | Kandy | Kandy | Jayawansa Construction (Pvt) Ltd | 5% | 67935586.77 | 64393315.7 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-17 | 2027-03-18