## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/SAB/KEG/KEG/14 | Rehabilitation / Improvement of Damaged Locations in Colombo Kandy Road from 56+050-98+950 | Kegalle | Kegalle | Tudawe Brothers (Pvt) Ltd | 65% | 261228130.78 | 267884733.58 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-07 | 2026-08-05 | 2026-08-06
RDA/DRP/SAB/KEG/KEG/16 | Rehabilitation / Improvement of Kegalle Siyambalapitiya Dewalegama Road, Polgahawela Kegalle Road and Mawanella Aranayaka Horewela Road | Kegalle | Kegalle | Creates Consultant and Construction | 60% | 258281578.64 | 278060284.2 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-18 | 2026-08-16 | 2026-08-16
RDA/DRP/SAB/KEG/RUW/29 | Rehabilitation / Improvement of Dehiowita - Daraniyagala - Nooriya Road (From 13+845 to 23+850) | Kegalle | Kegalle | SSP Engineers (Pvt) Ltd | 70% | 217629047.45 | 227460547.85 | Awarded | Emergency | Yes | Yes | Yes | 2026-03-25 | 2026-06-25 | 2026-07-29
RDA/DRP/SAB/KEG/KEG/13 | Rehabilitation / Improvement of damage locations at Ambepussa Kurunegala Trincomalee Road, Warakapola Kandalama Road, Warakapola Buypass Road, Morontota Arandara Road, Galigamuwa Ruwanwella Road, Gevilipitiya Hettimulla Road, Kegalle Bulattkohupitiya, Karawanella Road, Mawanella Hemmathagama Gampola Road and Rambukkana Mawanella Road in Kegalle Executive Engineers Division. | Kegalle | Kegalle | Senarath Engineering (Pvt) Ltd | 75% | 247437818.24 | 258512761.66 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-29 | 2026-08-29 | 2026-08-29
RDA/DRP/SAB/KEG/RUW/28 | Rehabilitation / Improvement of Bulathkohupitiya Dedugala Road, Warakapola Ruwanwella Road, Alawathura- Yatapana - Kotiyakumbura Road and Avissawella - Hatton - Nuwaraeliya Road | Kegalle | Kegalle | Southern Group Civil Construction (Pvt) Ltd | 50% | 260537133.84 | 284539377.98 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-10 | 2026-09-11 | 2026-09-11
RDA/DRP/SAB/KEG/RUW/33R | Yatiyanthota - Poonagala - Meenagala Road (from 3+760 to 6+760) | Kegalle | Kegalle | KENT Engineering (Pvt) Ltd | 0% | 284248590.98 | 251822503.71 | Awarded | Emergency |  |  |  | 2026-09-11 | 2027-02-12
RDA/DRP/SAB/KEG/RUW/35 | Yatiyanthota - Poonagala - Meenagala Road (from 13+400 to 18+200) | Kegalle | Kegalle | Southern Group Civil Construction (Pvt) Ltd | 25% | 170714785.54 | 172314426.38 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-10 | 2026-09-11 | 2026-09-11
RDA/DRP/SAB/KEG/RUW/30 | Rehabilitation of Dehiovita - Daraniyagala - Nooriya Road (from 23+850 to 27+960) due to catastrophic disaster cyclone Ditwa | Kegalle | Kegalle | Accon Engineering (Pvt) Ltd | 68% | 169223910.8 | 179826720.59 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-22 | 2026-08-21 | 2026-08-21
RDA/DRP/SAB/KEG/RUW/31 | Rehabilitation of Kegalle - Bulathkohupitiya - Karawanella Road due to catastrophic disaster cyclone Ditwa | Kegalle | Kegalle | Tudawe Brothers (Pvt) Ltd | 18% | 269890586.86 | 284390126.9 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-01 | 2026-08-31 | 2026-08-31