## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/CEN/NUE/NUE/60R | Rehabilitation / Improvement of Peradeniya Badulla Chenkaladi Road (A005) (40+750 - 42+850) | Nuwara Eliya | Nuwara Eliya | KSJ Construction (Pvt) Ltd | 10% | 336313078.73 | 338287510.33 | Awarded | Emergency | Yes | Yes | Yes | 2026-10-07 | 2027-04-06
RDA/DC/DRP/CP/NE/NE/04 | REHABILITAION/ IMPROVEMENTS OF LADY MACALUMS DRIVE ROAD (2+850 - 5+600KM) | Nuwara Eliya | Nuwara Eliya | KDA Weerasinghe & Co (Pvt) Ltd | 1% | 636338397 | 560630000 | Awarded | DC - Roads | Yes | Yes | Yes | 2026-09-17 | 2028-03-15