## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/EAS/TRI/TRI/06 | Rehabilitation / Improvement of Trincomalee - Pulmoddai Road (47+500 - 49+500) | Trincomalee |  | Southern Group Civil Construction (Pvt) Ltd | 20% | 131314798.09 | 138997580.74 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-06 | 2026-11-02 | 2026-11-02
RDA/DRP/EAS/TRI/TRI/07 | Rehabilitation / Improvement of Retaining Walls of Bridges at Upparu, Ralkuli, and Gangai | Trincomalee |  | Nathans Construction | 82% | 85089780.29 | 99606470.35 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-06 | 2026-11-02 | 2026-11-02
RDA/DRP/EAS/BAT/BAT/01 | Rehabilitation / Improvement and Surfacing from 56+900 km to 58+300km and from 58+640 km to 59+440 km on Bitticaloa - Thurukkondamadu - Trincomalee Road | Batticaloa |  | S S K Construction | 70% | 113074919.76 | 144552679.21 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-25 | 2026-08-24
RDA/DRP/EAS/TRI/TRI/03 | Rehabilitation / Improvement of Town & Gravets Road (B140) (Fort Fredrick Road) (0+020 - 0+210) | Trincomalee |  | Motec Engineering & Construction | 40% | 37828051.78 | 42948657.31 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-02 | 2026-12-01
RDA/DRP/EAS/TRI/TRI/04 | Rehabilitation / Improvement of Town & Gravets Road (B140) (Inner Harbour Road) (0+200 - 0+560) | Trincomalee |  | Motec Engineering & Construction | 65% | 40407339.17 | 45878059.68 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-02 | 2026-08-04
RDA/DRP/EAS/AMP/AMP/01 | Rehabilitation / Improvement of Ampara Uhana Mahoya Road (from 2+400 to 2+800) & (from 3+700 to 3+900), Siyambalanduwa Damana Ampara Road (from 43+000 to 45+000), (from 33+000 to 34+000), (from 35+500 to 36+500) & (from 52+000 to 53+000) and Chadayanthalawa Uhana Road (from 11+100 to 11+500) | Ampara |  | Ediriweera Construction | 90% | 27878955.02 | 31793559.86 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-09-10
RDA/DRP/EAS/AKK/AKK/04 | Rehabilitation / Improvement of Newguna – Manikkamadu – Irakkamam Road (0+000-1+250) & (1+300-2+600), Akkaraipattu Degavapi Vangamam Road (8+500-21+500) and Reconstruction of Culvert No. 368/2 on Colombo-Ratnapura-Wellawaya-Batticaloa Road | Ampara |  | Jeezan Trading and Transport | 29% | 171572395.05 | 196038211.02 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-12-10 | 2026-12-10
RDA/DRP/EAS/AKK/KAL/05 | Rehabilitation / Improvement and Reconstruction of Box Culvert at 9+780, Construction of Mass Concrete Retaining Wall (9+550 -9+600) & (9+600-11+000) on Sammanthurai - Malkampiddi - Deegawapi Road, Construction of Concrete Drain & rock blasting with utility shifting on Varaipathanchenai - Deegawapi Road (0+880 - 0+980 RHS), Construction of Concrete Drain on Deegawapi Temple Road (1+100 1+230 RHS), Construction of Mass Concete Retaining wall on Ampilanthurai - Veeramunai Road (25+600 - 26+000 LHS & RHS), Reconstruction of Wing Walls (at 375/2, 375/3, 375/4, 375/6) & Construction of Concrete Drain (384+000-389+000) on Colombo Ratnepura Wellawaya Batticoala Road, Construction of Concrete Drain (15+400 - 15+550 LHS) on Karaitivu - Ampara Road, Construction of Mass Concete Retaining Wall (5+700 -5+730) & on Construction of Hard Shoulder (Concrete) (13+200 - 13+600 LHS & RHS Selected Section) on Weeragoda - Central Camp Road, Construction of Hard Shoulder (Concete) (0+600 - 0+800 LHS & RHS) on Approach Road to Public Buildings | Ampara |  | Nazeeha Hardware and Construction | 23% | 196448155.48 | 236184712.99 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-12-10 | 2026-12-10
RDA/DRP/EAS/TRI/TRI/08 | REHABILITATION/ IMPROVEMENT OF ALLAI - KANTALE(B010) ROAD, SHOULDER & RETAINING WALL CONSTRUCTION FROM CHAINAGE 24+000 TO 34+500 | Trincomalee | Trincomalee | A.D.M Construction | 0% | 49212342.69 | 51740824.32 | Awarded | Emergency