## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/NWP/KURU/KULI/01R | Rehabilitation / Improvement of Selected Sections on Pannala Kuliyapitiya Road (B356) (0+000-6+000), Dandagamuwa Udawela Road (B088) (4+000 - 6+000), Marawila Udubaddawa Road (B272) (11+000 - 12+000), Kurunegala Narammala Madampe Road (B247) (52+000 - 54+000), Narammala Dankotuwa Road (B308) (16+000-37+000) and Alawwa Maharagama Road (B009) (1+000 - 14+200) in Kuliyapitiya EE Division | Kurunegala | Kurunegala | Can Construction and Consultancy (Pvt) Ltd | 12% | 181456551.09 | 0 | Awarded | Emergency | Yes | Yes | Yes | 2026-08-28 | 2026-12-25
RDA/DRP/NWP/KURU/KURU/02R | Rehabilitation / Improvement and Structure Improvement of Mallawapitiya Rambodagalla Keppitigala Road (30+943 - 33+858), Katugasthota Kurunegala Puttalam Road (AA010) (30+000 - 34+600) and Mawathagama Muwankanda Road (B281) (0+000 - 7+000) | Kurunegala | Kurunegala | Can Construction and Consultancy (Pvt) Ltd | 0% | 208660417.21 | 192045728.78 | Awarded | Emergency |  |  |  | 2026-09-11 | 2027-03-11
RDA/DRP/NWP/KURU/KURU/03R | Rehabilitation / Improvement of Thalgodapitiya Yatawaththa Road (B409) (9+100 - 14+650) | Kurunegala | Kurunegala | Jayawansa Construction (Pvt) Ltd | 0% | 129109243.85 | 117113346.84 | Awarded | Emergency |  |  |  | 2026-09-29 | 2027-03-29
RDA/DRP/NWP/KURU/KURU/04 | Rehabilitation / Improvement of Muththettugala Hiripitiya Road (B300) (10+880 - 11+080) & Vilakatupotha Ganewatta Kumbukgete road (B478) (9+100 - 9+400) | Kurunegala | Kurunegala | TMC Construction (Pvt) Ltd | 62% | 97503423.17 | 105193927.73 | Awarded | Emergency | Yes | Yes | Yes | 2026-04-21 | 2026-07-22 | 2026-07-22
RDA/DRP/NWP/KURU/MAHO/05 | Rehabilitation / Improvement of Galgamuwa - Nikawewa Road (B126) (6+000-20+000), Danikithawa - Ambanpola Road (B089) (20+925 - 21+000), Nikaweratiya - Moragollagama - Siyambalangamuwa Road (B326) (40+760 - 48+240), Malsiripura - Rambe Road (B610) (7+500 - 9+650), Ibbagamuwa - Kumbukgate - Madagalla Road (B159) (16+450 - 28+680), Hiripitiya - Galtenwewa Road (B609) (9+580-9+680), Padeniya - Anuradapura Road (AA028) (8+480-8+800) and Katugasthota - Kurunegala - Puththalama Road (AA010) (73+745-73 -870) in Maho EE Division | Kurunegala | Kurunegala | St. Anthony's Construction | 70% | 151515024.36 | 166163663.09 | Awarded | Emergency | Yes | Yes | Yes | 2026-05-05 | 2026-09-01 | 2026-09-01
RDA/DRP/NWP/KURU/MAHO/06R | Rehabilitation / Improvement of Kadigawa Bridge Approaches on Pahala Mawathagama - Kadigawa Road (0+000-0+175) | Kurunegala |  | RCDC Construction Company (Pvt) Ltd | 6% | 75025358.95 | 60148814.16 | Awarded | Emergency | Yes | Yes | Yes | 2026-10-07 | 2027-02-09
RDA/DRP/NWP/CHI/CHI/08 | Rehabilitation / Improvement of Baththuluoya - Udappuwa - Andimunai Road (B614) at 6+100 in Chilaw EE Division | Puttalam | Chilaw | ST MARY Construction | 56% | 83944711.21 | 84197870.47 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-12 | 2026-08-15 | 2026-10-14
RDA/DRP/NWP/CHI/CHI/07 | Rehabilitation / Improvement of Nainamadama – Iranavila - Chilaw Road (B640) (6+200 - 32+200), Bangadeniya - Adigama – Anamaduwa Road (B045) (2+200 - 13+400) and Peliyagoda - Puttala Road (A003) (78+100 - 93+200) in Chilaw EE Division | Puttalam | Chilaw | Jayawansa Construction (Pvt) Ltd | 28% | 214608362.18 | 248319499.59 | Awarded | Emergency | Yes | Yes | Yes | 2026-07-22 | 2027-01-20
RDA/DRP/NWP/CHI/PUT/10 | Rehabilitation / Improvement of Palavi - Kalpitiya Road (B349) and Etalai - Talawila (Jubily Mawatha) Road (B516) (0+900-1+200) Puttalam EE Division | Puttalam | Chilaw | ST MARY Construction | 14% | 136011633.11 | 147930527.03 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-02 | 2026-12-01
RDA/DRP/NWP/CHI/PUT/11 | Rehabilitation / Improvement of Town Roads (Saltern Road, Marikkar Street, Poles Road, Rest House Road, Good Shed Road) and Puttalam Trincomalee Road (AA012) in Puttalam EE Division | Puttalam | Chilaw | Omega Construction Company (Pvt) Ltd | 35% | 303043337.3 | 290051718.48 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-02 | 2026-12-01
RDA/DRP/NWP/CHI/PUT/12 | Rehabilitation / Improvement of Puttalam Marichchikaddi Road in Puttalam 6+100-9+000 | Puttalam | Chilaw | Omega Construction Company (Pvt) Ltd | 26% | 141404654.67 | 143347737.52 | Awarded | Emergency | Yes | Yes | Yes | 2026-06-18 | 2026-12-17