## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/NOR/MUL/KIL/07 | Rehabilitation / Improvement of Sholder of 1. Kandy - Jaffna Road (251+000 - 252+200), 2.0Kandy - Jaffna Road (260+000 - 270+000), 3.Nawatkuly - Kerativu - Mannar Road(54+000 - 57+000), 4.Paranthan - Karachchi - Mullaitivu (0+000 - 1+000, 6+000- 8+000, 9+000-11+000, 12+500-14+500, 16+000-17+500, 19+400-19+800) 5.Paranthan - Ponakary Road (9+000-16+000) 6.Soranpattu - Thalaiyadi road (2+500-5+000) | Kilinochchi |  | SSK Construction | 7% | 62162612.7 | 55617040.01 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-07 | 2026-12-07
RDA/DRP/NOR/VOU/MAN/08 | Rehabilitation / Improvement of 85/3 Bridge Approach Reconstruction with Gabion Walls & Damaged Shoulder Construction in between Ch (65+500-79+150km) and Reconstruction of Embankment, shoulder & Improvement to Concrete Shoulder on Navatkuli-Kerativu-Mannar Road (AA032) | Mannar |  | Asset Engineering (Pvt) Ltd | 10% | 98477554.94 | 86662670.95 | Awarded | Emergency | Yes | Yes | Yes | 2026-08-27 | 2026-12-23
RDA/DRP/NOR/MUL/MUL/09 | Rehabilitation /Improvement & Rectification of flood damages in Mullaitivu ( Mankulam-Mullaitivu Road (AA034), Mankulam-Vellankulam Road (B269), Mullaitivu-Kokkilai Road (B297), Kandy-Jaffna Road (AA009), Paranthan-Karachchi-Mullaitivu Road (AA035)) | Mullaitivu | Mullaitivu | Jana Civil Work Contractors & Material Suppliers | 12% | 37338982.74 | 50474039.9 | Awarded | Emergency | Yes | Yes | Yes | 2026-08-27 | 2026-11-25
RDA/DRP/NOR/VOU/VOU/15 | Rehabilitation /Improvement of Kandy-Jaffna Road (AA009) & Madawachchiya-Mannar-Thalaimannar Road (AA014) | Vavuniya | Vavuniya | Jana Civil Work Contractors & Material Suppliers | 19% | 42832926.51 | 46307621.71 | Awarded | Emergency | Yes | Yes | Yes | 2026-08-27 | 2026-12-23