## Awarded Projects
Contract No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RDA/DRP/SAB/KEG/RUW/34R | Yatiyanthota - Poonagala - Meenagala Road (from 6+760 to 9+000) | Kegalle | Kegalle | KENT Engineering (Pvt) Ltd | 0% | 301661961.22 | 292200028.87 | Awarded | Emergency |  |  |  | 2026-09-11 | 2027-03-12
RDA/DRP/SAB/RAT/EMB/03R | Rehabilitation / Improvement of Embilipitiya - Panamura - Buluthota Road (0+000-39+000) | Ratnapura | Ratnapura | Samarasinghe Construction Pvt Ltd | 3% | 288699729.18 | 294962216.95 | Awarded | Emergency | Yes | Yes | Yes | 2026-09-11 | 2027-03-12