## Financial Dashboard
Contract No | Contract Amount | Advance Paid (excl.) | Advance Paid (incl.) | Advance Pend (excl.) | Advance Pend (incl. VAT) | IPCs Paid (excl.) | IPCs Paid (incl.) | IPCs Pend (excl.) | IPCs Pend (incl. VAT) | Financial Progress (Mn) | Financial Progress (%) | Fin. Prog. w/ Out. (Mn) | Fin. Prog. w/ Out. (%)
RDA/DRP/CEN/KDY/KAD/11 | 193404194.96 | 33346525.54 | 39348900.14 | 0 | 0 | 2776135.64 | 3275840.06 | 0 | 0 | 42.6247 | 18.7% | 42.6247 | 18.7%
RDA/DRP/CEN/KDY/KAN/14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
RDA/DRP/CEN/KDY/KUN/20 | 31558227.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
RDA/DRP/CEN/KDY/KUN/21 | 257721453.96 | 46231491.42 | 54553159.88 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5532 | 17.9% | 54.5532 | 17.9%
RDA/DRP/CEN/KDY/KUN/22 | 224968435.78 | 40192882.63 | 47427601.5 | 0 | 0 | 0 | 0 | 0 | 0 | 47.4276 | 17.9% | 47.4276 | 17.9%
RDA/DRP/CEN/KDY/KUN/25 | 157909825.01 | 28346587.8 | 33448973.6 | 0 | 0 | 0 | 0 | 0 | 0 | 33.449 | 18% | 33.449 | 18%
RDA/DRP/CEN/KDY/KUN/27 | 113434139.4 | 0 | 0 | 20128022.37 | 23751066.4 | 0 | 0 | 0 | 0 | 0 | 0% | 23.7511 | 17.7%
RDA/DRP/CEN/KDY/KUN/29 | 91559621.04 | 16157282.84 | 19065593.75 | 0 | 0 | 0 | 0 | 5944519.21 | 7014532.67 | 19.0656 | 17.6% | 26.0801 | 24.1%
RDA/DRP/CEN/MTL/MTL/32 | 292279354.08 | 52461047.84 | 61904036.46 | 0 | 0 | 0 | 0 | 4463153.84 | 5266521.53 | 61.904 | 17.9% | 67.1706 | 19.5%
RDA/DRP/CEN/MTL/MTL/33 | 165006430.79 | 29068239.71 | 34300522.86 | 0 | 0 | 0 | 0 | 0 | 0 | 34.3005 | 17.6% | 34.3005 | 17.6%
RDA/DRP/CEN/MTL/MTL/35 | 266607902.15 | 46351528.36 | 54694803.46 | 0 | 0 | 0 | 0 | 0 | 0 | 54.6948 | 17.4% | 54.6948 | 17.4%
RDA/DRP/CEN/MTL/MTL/38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
RDA/DRP/CEN/MTL/NAL/49 | 44706119.13 | 7270523.42 | 8579217.63 | 0 | 0 | 0 | 0 | 5063036.56 | 5794383.14 | 8.5792 | 16.3% | 14.3736 | 27.6%
RDA/DRP/CEN/MTL/NAL/51 | 17458592.78 | 2700844.13 | 3186956.07 | 0 | 0 | 0 | 0 | 2081765.34 | 2456483.12 | 3.187 | 15.5% | 5.6434 | 27.4%
RDA/DRP/CEN/NUE/HAN/57 | 47755538.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
RDA/DRP/CEN/NUE/NUE/66 | 161841095.7 | 28951653.76 | 34162951.44 | 0 | 0 | 14629744.09 | 17263098.02 | 0 | 0 | 51.426 | 26.9% | 51.426 | 26.9%
RDA/DRP/CEN/NUE/NUE/67 | 239417811.34 | 43196511.18 | 50971883.16 | 0 | 0 | 23041263.85 | 27188691.84 | 0 | 0 | 78.1606 | 27.7% | 78.1606 | 27.7%
RDA/DRP/CEN/NUE/NUE/68 | 213999600.01 | 38371088.02 | 45277883.86 | 0 | 0 | 0 | 0 | 0 | 0 | 45.2779 | 17.9% | 45.2779 | 17.9%
RDA/DRP/CEN/NUE/NUE/69 | 266045892.19 | 47095300 | 55572454 | 0 | 0 | 18867467.5 | 22263611.65 | 10979182.13 | 12955434.92 | 77.8361 | 24.8% | 90.7915 | 28.9%
RDA/DRP/CEN/NUE/NUE/86 | 33765626.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
RDA/DRP/CEN/NUE/NUR/97 | 93758217.76 | 0 | 0 | 14149694.34 | 16696639.33 | 0 | 0 | 0 | 0 | 0 | 0% | 16.6966 | 15.1%
RDA/DRP/CEN/NUE/NUR/98 | 188617394.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
RDA/DRP/CEN/NUE/NUR/101 | 86746198.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
RDA/DC/DRP/CP/NE/NRW/02 | 374859845.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%