## Awarded Projects
Contract No. | Road Name | District | EE Division | Contractor | Progress (%) | Contract Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Commenced | Scheduled End
RDA/DRP/CEN/MTL/MTL/32 | Kandy Jaffna Road A 009 (17+710 - 46+450), Thalgodapitiya Yatawatta Dombawela road B 409 (15+030 - 26+800),Palapathwela Galewela road B 346 (0+000 - 8+100) | Matale | Matale | Lahiru Construction and Consultants (Pvt) Ltd | 61% | 292279354.08 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/MTL/MTL/33 | Wattegama Matale Road B 462,Approch road to Ukuwela Railway station B 027 | Matale | Matale | Jayasinghe Construction (Pvt) Ltd | 23% | 165006430.79 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-05-02 | 2026-07-31
RDA/DRP/CEN/MTL/MTL/35 | Rattota Gammaduwa Road B 392 | Matale | Matale | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 56% | 266607902.15 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/MTL/MTL/38 | Kalalpitiya Ukuwela Elkaduwa Road | Matale | Matale |  | 5% | 0 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-07-30 | 2027-01-27