## Awarded Projects
Contract No. | Road Name | District | EE Division | Contractor | Progress (%) | Contract Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Commenced | Scheduled End
RDA/DRP/CEN/NUE/NUE/66 | Nuwara Eliya Town Road (B331) | NuwaraEliya | NuwaraEliya | KSJ Construction (Pvt) Ltd | 58% | 161841095.7 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-05-02 | 2026-07-31
RDA/DRP/CEN/NUE/NUE/67 | Harangala - Kalapitiya - Kumbaloluwa Road (B148) | NuwaraEliya | NuwaraEliya | KSJ Construction (Pvt) Ltd | 62% | 239417811.34 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/68 | Thawalanthenna Thalawakelle Road (B412) | NuwaraEliya | NuwaraEliya | Green Scene Construction (Pvt) Ltd | 27% | 213999600.01 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/69 | Ulapane Pussallawa Road (B431) | NuwaraEliya | NuwaraEliya | Southern group civil construction (Pvt) Ltd | 45% | 266045892.19 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/86 | Approch road to R'way station (Watagoda) Road | NuwaraEliya | NuwaraEliya | Pragathi Civil Construction | 8% | 33765626.86 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-06-12 | 2026-09-10