## Awarded Projects
Contract No. | Road Name | District | EE Division | Contractor | Progress (%) | Contract Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Commenced | Scheduled End
RDA/DRP/CEN/NUE/NUR/97 | Nawalapitiya Ginigathena Road (B-319) | NuwaraEliya | Norwood | Jayawansa Construction (Pvt) Ltd | 26% | 93758217.76 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-06-17 | 2026-09-15
RDA/DRP/CEN/NUE/NUR/98 | Harangala Kalapitiya Road (B-148) (0+000-10+700), Approach Road to Harangala Dam Crest Road (B-491) (0+000-3+820), Nawalapitiya Harangala Road (B-306) (0+000-10+700) | NuwaraEliya | Norwood | Pragathi Civil Construction | 12% | 188617394.68 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-06-18 | 2026-12-16
RDA/DRP/CEN/NUE/NUR/101 | Hatton Maskeliya Delhouse Road (B-149) | NuwaraEliya | Norwood | Sooriya Builders | 3% | 86746198.17 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-06-18 | 2026-11-11
RDA/DC/DRP/CP/NE/NRW/02 | REHABILITATION/ IMPROVEMENT OF APPROACH ROAD TO LAXAPANA POWER HOUSE ROAD CH (6+100 TO 12+000) KM | NuwaraEliya | Norwood | U.K.S Lanka Engineering (Pvt) Ltd | 2% | 374859845.1 | Awarded | Tender by Director Construction | Yes | Yes | Yes | 2026-07-30 | 2027-07-29