## Awarded Projects
Contract No. | Road Name | District | EE Division | Contractor | Progress (%) | Contract Amount (LKR) | Status | Category | Mobilized | Kick Off | Active | Commenced | Scheduled End
RDA/DRP/CEN/KDY/KAD/11 | Nawalapitiya - Dolosbage Road ( B -318) ( 10+500 - 19+350 ), Dedugala Dolosbage Road ( B -588) ( 10+100 - 12+410 ) | Kandy | Kadugannawa | Tiasa Construction (Pvt) Ltd | 0% | 193404194.96 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-03-25 | 2026-09-23
RDA/DRP/CEN/KDY/KAN/14 | Katugasthota Medawala road ( B 0206)( 0 + 000 - 9+370) | Kandy | Kandy |  | 0% | 0 | Awarded | Emergency Projects |  |  |  | 2026-09-01 | 2027-03-01
RDA/DRP/CEN/KDY/KUN/20 | Rehabilitation / Improvement to Structures on Madolkelle - Kabaragala - Kandenuwara Road (B 257) (4+000 - 8+000) | Kandy | Kundasale | Samindra Construction | 17% | 31558227.98 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-07-20 | 2026-11-15
RDA/DRP/CEN/KDY/KUN/21 | Pitiyegedara-Waththegama-Iriyagasthenna Road (B369) | Kandy | Kundasale | Jayasinghe Construction (Pvt) Ltd | 9% | 257721453.96 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-04-30 | 2026-10-28
RDA/DRP/CEN/KDY/KUN/22 | Weraganthota-Randenigala Road (B474) | Kandy | Kundasale | SD Civil Construction (Pvt) Ltd | 35% | 224968435.78 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-03-25 | 2026-09-23
RDA/DRP/CEN/KDY/KUN/25 | Katugastota - Madawala - Bamberella Road | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 26% | 157909825.01 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-07-06 | 2026-11-01
RDA/DRP/CEN/KDY/KUN/27 | Kandy - Jaffna Road | Kandy | Kundasale | Gihan Enterpriese | 30% | 113434139.4 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-06-30 | 2026-10-27
RDA/DRP/CEN/KDY/KUN/29 | Kandy - Mahiyanganaya - Padiyaththalawa Road (24+000-71+500) A026 and Moragahamula victoria damtop B493 | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 21% | 91559621.04 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-07-06 | 2027-01-03
RDA/DRP/CEN/MTL/MTL/32 | Kandy Jaffna Road A 009 (17+710 - 46+450), Thalgodapitiya Yatawatta Dombawela road B 409 (15+030 - 26+800),Palapathwela Galewela road B 346 (0+000 - 8+100) | Matale | Matale | Lahiru Construction and Consultants (Pvt) Ltd | 61% | 292279354.08 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/MTL/MTL/33 | Wattegama Matale Road B 462,Approch road to Ukuwela Railway station B 027 | Matale | Matale | Jayasinghe Construction (Pvt) Ltd | 23% | 165006430.79 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-05-02 | 2026-07-31
RDA/DRP/CEN/MTL/MTL/35 | Rattota Gammaduwa Road B 392 | Matale | Matale | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 56% | 266607902.15 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/MTL/MTL/38 | Kalalpitiya Ukuwela Elkaduwa Road | Matale | Matale |  | 5% | 0 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-07-30 | 2027-01-27
RDA/DRP/CEN/MTL/NAL/49 | Naula- Elahera-Pallegama-Hettipola Road (B-312) (8+200-61+240) | Matale | Nalanda | Platinum Holdings Lanka (Private) Limited | 65% | 44706119.13 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-06-18 | 2026-11-18
RDA/DRP/CEN/MTL/NAL/51 | Bowathenna Access Road (B-064) (0+000-2+410) | Matale | Nalanda | Platinum Holdings Lanka (Private) Limited | 65% | 17458592.78 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-06-18 | 2026-10-14
RDA/DRP/CEN/NUE/HAN/57 | Keerthibandarapura Naranthalawa Road ( B -511 ) ( 0+000 - 4+100 ) | NuwaraEliya | Hanguranketha | Samindra Construction | 2% | 47755538.96 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-07-30 | 2026-10-28
RDA/DRP/CEN/NUE/NUE/66 | Nuwara Eliya Town Road (B331) | NuwaraEliya | NuwaraEliya | KSJ Construction (Pvt) Ltd | 58% | 161841095.7 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-05-02 | 2026-07-31
RDA/DRP/CEN/NUE/NUE/67 | Harangala - Kalapitiya - Kumbaloluwa Road (B148) | NuwaraEliya | NuwaraEliya | KSJ Construction (Pvt) Ltd | 62% | 239417811.34 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/68 | Thawalanthenna Thalawakelle Road (B412) | NuwaraEliya | NuwaraEliya | Green Scene Construction (Pvt) Ltd | 27% | 213999600.01 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/69 | Ulapane Pussallawa Road (B431) | NuwaraEliya | NuwaraEliya | Southern group civil construction (Pvt) Ltd | 45% | 266045892.19 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-05-02 | 2026-10-30
RDA/DRP/CEN/NUE/NUE/86 | Approch road to R'way station (Watagoda) Road | NuwaraEliya | NuwaraEliya | Pragathi Civil Construction | 8% | 33765626.86 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-06-12 | 2026-09-10
RDA/DRP/CEN/NUE/NUR/97 | Nawalapitiya Ginigathena Road (B-319) | NuwaraEliya | Norwood | Jayawansa Construction (Pvt) Ltd | 26% | 93758217.76 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-06-17 | 2026-09-15
RDA/DRP/CEN/NUE/NUR/98 | Harangala Kalapitiya Road (B-148) (0+000-10+700), Approach Road to Harangala Dam Crest Road (B-491) (0+000-3+820), Nawalapitiya Harangala Road (B-306) (0+000-10+700) | NuwaraEliya | Norwood | Pragathi Civil Construction | 12% | 188617394.68 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-06-18 | 2026-12-16
RDA/DRP/CEN/NUE/NUR/101 | Hatton Maskeliya Delhouse Road (B-149) | NuwaraEliya | Norwood | Sooriya Builders | 3% | 86746198.17 | Awarded | Emergency Projects | Yes | Yes | Yes | 2026-06-18 | 2026-11-11
RDA/DC/DRP/CP/NE/NRW/02 | REHABILITATION/ IMPROVEMENT OF APPROACH ROAD TO LAXAPANA POWER HOUSE ROAD CH (6+100 TO 12+000) KM | NuwaraEliya | Norwood | U.K.S Lanka Engineering (Pvt) Ltd | 2% | 374859845.1 | Awarded | Tender by Director Construction | Yes | Yes | Yes | 2026-07-30 | 2027-07-29