## Progress Ministry
Progress status - Ditwah
Date | 2026-09-07
Serial No | Tender Batch No | Contract No | District | EE Division | Contractor | Project Duration (Days) | Planned Work Start Date | Planned Work Finish Date | LOA Issued? (Yes/No) | Agreement? (Yes/No) | Account Open? (Yes/No) | Advance Paid? (Yes/No) | Kick Off? (Yes/No) | Mobilized to site (Yes/No) | In Progress (Yes/No) | Actual Progress % (Physical) | Financial Progress (Mn) | Critical Issues
11 | 3 | RDA/DRP/CEN/KDY/KAD/11 | Kandy | Kadugannawa | Tiasa Construction (Pvt) Ltd | 182 | 2026-03-25 | 2026-09-23 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0 | 42.62
14 |  | RDA/DRP/CEN/KDY/KAN/14 | Kandy | Kandy |  | 182 | 2026-09-01 | 2027-03-01 | Yes | [6 empty] | 0 | 0
20 |  | RDA/DRP/CEN/KDY/KUN/20 | Kandy | Kundasale | Samindra Construction | 119 | 2026-07-20 | 2026-11-15 | Yes | Yes |  | No | Yes | Yes | Yes | 17 | 0
21 | 4 | RDA/DRP/CEN/KDY/KUN/21 | Kandy | Kundasale | Jayasinghe Construction (Pvt) Ltd | 182 | 2026-04-30 | 2026-10-28 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 9 | 54.55 | In the process of Termination
22 | 4 | RDA/DRP/CEN/KDY/KUN/22 | Kandy | Kundasale | SD Civil Construction (Pvt) Ltd | 182 | 2026-03-25 | 2026-09-23 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 35 | 47.43
25 | 12 | RDA/DRP/CEN/KDY/KUN/25 | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 119 | 2026-07-06 | 2026-11-01 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 26 | 33.45 | NOT YET MOBILIZED
27 | 12 | RDA/DRP/CEN/KDY/KUN/27 | Kandy | Kundasale | Gihan Enterpriese | 119 | 2026-06-30 | 2026-10-27 | Yes | Yes | Yes |  | Yes | Yes | Yes | 30 | 0 | NOT YET MOBILIZED
29 | 12 | RDA/DRP/CEN/KDY/KUN/29 | Kandy | Kundasale | S N O Builders (Pvt) Ltd | 182 | 2026-07-06 | 2027-01-03 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 21 | 19.07 | NOT YET MOBILIZED
32 | 3 | RDA/DRP/CEN/MTL/MTL/32 | Matale | Matale | Lahiru Construction and Consultants (Pvt) Ltd | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 61 | 61.9
33 | 4 | RDA/DRP/CEN/MTL/MTL/33 | Matale | Matale | Jayasinghe Construction (Pvt) Ltd | 91 | 2026-05-02 | 2026-07-31 | Yes | Yes | No | Yes | Yes | Yes | Yes | 23 | 34.3 | In the process of Termination
35 | 4 | RDA/DRP/CEN/MTL/MTL/35 | Matale | Matale | Kanwel Constructions & Civil Engineering (Pvt) Ltd | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes |  | Yes | Yes | Yes | Yes | 56 | 54.69
38 | 12 | RDA/DRP/CEN/MTL/MTL/38 | Matale | Matale |  | 182 | 2026-07-30 | 2027-01-27 | Yes |  |  |  | Yes | Yes | Yes | 5 | 0
49 | 11 | RDA/DRP/CEN/MTL/NAL/49 | Matale | Nalanda | Platinum Holdings Lanka (Private) Limited | 154 | 2026-06-18 | 2026-11-18 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 65 | 8.58
51 | 11 | RDA/DRP/CEN/MTL/NAL/51 | Matale | Nalanda | Platinum Holdings Lanka (Private) Limited | 119 | 2026-06-18 | 2026-10-14 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 65 | 3.19
57 | 12 | RDA/DRP/CEN/NUE/HAN/57 | NuwaraEliya | Hanguranketha | Samindra Construction | 91 | 2026-07-30 | 2026-10-28 | Yes |  |  |  | Yes | Yes | Yes | 2 | 0
66 | 3 | RDA/DRP/CEN/NUE/NUE/66 | NuwaraEliya | NuwaraEliya | KSJ Construction (Pvt) Ltd | 91 | 2026-05-02 | 2026-07-31 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 58 | 51.43
67 | 3 | RDA/DRP/CEN/NUE/NUE/67 | NuwaraEliya | NuwaraEliya | KSJ Construction (Pvt) Ltd | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 62 | 78.16
68 | 4 | RDA/DRP/CEN/NUE/NUE/68 | NuwaraEliya | NuwaraEliya | Green Scene Construction (Pvt) Ltd | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 27 | 45.28
69 | 4 | RDA/DRP/CEN/NUE/NUE/69 | NuwaraEliya | NuwaraEliya | Southern group civil construction (Pvt) Ltd | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 45 | 77.84
86 | 10 | RDA/DRP/CEN/NUE/NUE/86 | NuwaraEliya | NuwaraEliya | Pragathi Civil Construction | 91 | 2026-06-12 | 2026-09-10 | Yes |  |  |  | Yes | Yes | Yes | 8 | 0
97 | 10 | RDA/DRP/CEN/NUE/NUR/97 | NuwaraEliya | Norwood | Jayawansa Construction (Pvt) Ltd | 91 | 2026-06-17 | 2026-09-15 | Yes | Yes | Yes |  | Yes | Yes | Yes | 26 | 0
98 | 10 | RDA/DRP/CEN/NUE/NUR/98 | NuwaraEliya | Norwood | Pragathi Civil Construction | 182 | 2026-06-18 | 2026-12-16 | Yes |  |  |  | Yes | Yes | Yes | 12 | 0
101 | 10 | RDA/DRP/CEN/NUE/NUR/101 | NuwaraEliya | Norwood | Sooriya Builders | 147 | 2026-06-18 | 2026-11-11 | Yes |  |  |  | Yes | Yes | Yes | 3 | 0
102 |  | RDA/DC/DRP/CP/NE/NRW/02 | NuwaraEliya | Norwood | U.K.S Lanka Engineering (Pvt) Ltd | 365 | 2026-07-30 | 2027-07-29 | Yes |  |  |  | Yes | Yes | Yes | 2 | 0