## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/04/25/13/CP/KY | RR/RDA/04/25/13 | Gonaala Pasala Asala Sita Kubukkadura Athuru Margayak Wana Gurumada Margaya | Kandy | Kundasale | Dharshana Construction | 37% | 35195820 | 42644514.03 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-08 | 2026-08-21 | 2026-08-21
RR/RDA/04/25/19/CP/KY | RR/RDA/04/25/19 | Mulgama viduhala Asala sita lewalan dakwa | Kandy | Gampola | The Wise Lanka Construction Company (Pvt) Ltd | 35% | 25917512.5 | 46131296.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-14 | 2026-03-31
RR/RDA/04/25/20/CP/KY | RR/RDA/04/25/20 | Carpeting road Ratemulla to Wendesiwaththa End | Kandy | Kandy | Wiscon (Pvt) Ltd | 45% | 36995817.1 | 40119276.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-08 | 2026-02-05 | 2026-03-20
RR/RDA/04/25/21/CP/KY | RR/RDA/04/25/21 | Galaha group sita finas kotasa Pahalagama-Ihalagama haraha nawa rohala dakwa Margaya | Kandy | Gampola | UGD Constructions | 80% | 22711029 | 40719533.36 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-03-10
RR/RDA/04/25/25/CP/KY | RR/RDA/04/25/25 | Delgasthenna Road | Kandy | Kundasale | NAGMA ENGINEERING (PVT) LTD | 0% | 56035922.24 | 78736509.47 | Awarded | Tender Above 50Mn |  |  |  | 2026-01-01 | 2026-05-06 | 2026-05-31
RR/RDA/04/25/28/CP/KY | RR/RDA/04/25/28 | Dehideniya sita Hedeniya dakwa Margaya | Kandy | Kandy | Senerath Engineering (pvt) Ltd | 35% | 38495776 | 41827394.04 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-25 | 2026-01-23 | 2026-04-10
RR/RDA/04/25/31(1)/CP/KY | RR/RDA/04/25/31(1) | Paththunupitiya School road to Gampola Road through Pallegama Anguruwala | Kandy | Gampola | Central Engineering Services Pvt Ltd. (CESL) | 30% | 50476865.28 | 65989182.36 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-03 | 2026-07-07 | 2026-10-31
RR/RDA/04/25/41/CP/KY | RR/RDA/04/25/41 | Karyala handiya pahala margya concrete kirima | Kandy | Gampola | UGD Constructions | 85% | 22047564 | 39022781.94 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2026-01-14 | 2026-01-31
RR/RDA/04/25/52/CP/KY | RR/RDA/04/25/52 | Bokalawela Road from Hapugoda Junction to Ranawana (Drinage System Development and Road) | Kandy | Kandy | Senerath Engineering (pvt) Ltd | 60% | 50478905 | 72631674.77 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-21 | 2026-08-22
RR/RDA/04/25/53/CP/KY | RR/RDA/04/25/53 | Road from Amuvandeniya to Magurudeniya (development of the drainage and carpeting of the road) | Kandy | Kandy | Tiasa Construction (Pvt) Ltd | 40% | 29850460.2 | 39182935.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-08 | 2026-09-08
| RR/RDA/04/25/54 | Development of the Dolapihilla road from Navinnapitiya via Deldeniya | Kandy | Kandy | Ajith Construction | 20% | 65808186.5 | 73819405.52 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-06-08 | 2026-10-05
| RR/RDA/04/25/55 | Development of entrance roads, pedestrian rest areas and parking areas of the Sri Dalada Maligawa premises | Kandy | Kandy | Southern Group Civil Construction (Pvt) Ltd. | 40% | 83080000 | 98049399.56 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-06 | 2026-08-07
RR/RDA/05/25/09/CP/MTL | RR/RDA/05/25/09 | Ilukkumbura Samurdhi karyalaya asala Patti ela pilama dakwa | Matale | Matale | Pragathi Civil Contractor | 80% | 38748820 | 41365188.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-23 | 2026-02-15
RR/RDA/05/25/10/CP/MTL | RR/RDA/05/25/10 | Sonuththa pradana margaye Shailatharamaya idiriye sita 80 yaya dakwa | Matale | Nalanda | NAGMA ENGINEERING (PVT) LTD | 70% | 56167707.75 | 79104652.3 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-24 | 2026-04-27 | 2026-05-31
RR/RDA/05/25/11/CP/MTL | RR/RDA/05/25/11 | Hunukete sita Elagala dakwa Pradana Margaya | Matale | Matale | Senerath Engineering (pvt) Ltd | 50% | 82470143.89 | 108683600.82 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-06 | 2026-03-26 | 2026-05-20
RR/RDA/05/25/26/CP/MTL | RR/RDA/05/25/26 | Pallepola saukya karyalaye sita ekamuthugama dakwa margaya | Matale | Nalanda | Jayaru Engineering (Pvt) Ltd | 60% | 18760083.54 | 30575367.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-01 | 2025-12-31 | 2026-03-25
RR/RDA/05/25/30/CP/MTL | RR/RDA/05/25/30 | Ganadewi pilimaya asala Kulathunga mahathage welanda sala dakwa | Matale | Nalanda | Lahiru Construction & Consultants (PVT) Ltd | 60% | 59540000 | 77270301.29 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-10 | 2026-08-10 | 2026-08-10
RR/RDA/06/25/32/CP/NE | RR/RDA/06/25/32 | Nanuoya Glaso pahala kotasa Margaya | Nuwara Eliya | Nuwara Eliya | wiscon (pvt) ltd | 5% | 38841280.5 | 43085721.61 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-26 | 2026-05-20
RR/RDA/06/25/34/CP/NE | RR/RDA/06/25/34 | Udupussellawa margaye Amasta handiye sita Ambagasdowa dakwa Margaya | Nuwara Eliya | Hanguranketha | NAGMA ENGINEERING (PVT) LTD | 0% | 54639783.83 | 84599211.7 | Awarded | Tender Above 50Mn |  |  |  | 2026-01-01 | 2026-05-06
RR/RDA/06/25/38/CP/NE | RR/RDA/06/25/38 | Ketahira Gallella margya palama haraha Udagama dakwa Margaya | Nuwara Eliya | Hanguranketha | NAGMA ENGINEERING (PVT) LTD | 0% | 38465634.79 | 54713411.13 | Awarded | Tender Above 50Mn |  |  |  | 2026-01-01 | 2026-05-06
RR/RDA/06/25/40/CP/NE | RR/RDA/06/25/40 | Walapane Samachaithya asalin Arambawana Kurundu oya diyaella dakwa Margaya | Nuwara Eliya | Hanguranketha | UGD Constructions | 10% | 31672222.12 | 35044851.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-01-31
RR/RDA/06/25/41/CP/NE | RR/RDA/06/25/41 | Nayapana Gammada tharapara sanwardhanaya | Nuwara Eliya | Nuwara Eliya | Central Engineering Services Pvt Ltd. (CESL) | 35% | 51754603.52 | 64794731.2 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-28 | 2026-07-29
RR/RDA/06/25/42/CP/NE | RR/RDA/06/25/42 | AC Overlaying from Polpitiya Junction to 04th Mile Post (CH 3+700 – 8+700 km) | Nuwara Eliya | Norwood | UKS Lanka Engineering Pvt Ltd. | 50% | 220116957.84 | 276005265.17 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-11-24 | 2026-08-22 | 2026-08-22
| RR/RDA/06/25/45 | Carpeting of road from Bambaragama Moragollahinna to Karamidula | Nuwara Eliya | Hanguranketha | Ajith Construction | 10% | 61551869.38 | 68311664.39 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-05
| RR/RDA/06/25/46 | Carpeting of Mahathenna to Hapugasdeniya Main Road | Nuwara Eliya | Hanguranketha | Ajith Construction | 73% | 68070000 | 79957655.08 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-05
RR/RDA/16/25/03/AKK/AMP | RR/RDA/16/25/03 | Polbedda Junction to Galwalayaya Road | Ampara | Dehiaattakandiya | MOTEC Engineering & Construction | 52% | 17506335 | 24800970.39 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-10 | 2026-03-10 | 2026-03-16
RR/RDA/SP/16/25/01/AKK/AMP | RR/RDA/SP/16/25/01 | Rectification and Asphalt Surfacing on Ambahagawela -Namaloya Main Road | Ampara | Ampara | SMA Careem Engineering Consultancy Services & Suppliers (Pvt) Ltd | 34% | 222189859.13 | 306475548.92 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-31 | 2026-06-30
RR/RDA/STA II/16/25/03/AKK/AMP | RR/RDA/STA II/16/25/03 | Padiyathalawa Navinna road from Navinna Junction A5 to Navinna Bridge | Ampara | Dehiaattakandiya | Vithu Construction | 65% | 39470000 | 60426139.14 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-25 | 2026-05-26
RR/RDA/16/25/10KM/01/AKK/AMP | RR/RDA/16/25/10KM/01 | The road from the bridge near Ridee ela Temple to Island Plot No. 197 | Ampara | Dehiaattakandiya | Sawsiri Construction | 17% | 24113338.37 | 34027781.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-25 | 2026-05-26
RR/RDA/16/25/10KM/02/AKK/AMP | RR/RDA/16/25/10KM/02 | Road from Nelum Cafe Junction to Neeththa | Ampara | Ampara | Gama Construction & Consultant pvt Ltd | 20% | 19318560.1 | 29760217.62 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-07 | 2026-06-05
RR/RDA/16/25/10KM/03/AKK/AMP | RR/RDA/16/25/10KM/03 | On the road from Pulungasmulla to Padawala, the road from near Shanta Veladasala towards Padawala | Ampara | Dehiaattakandiya | Sawsiri Construction | 55% | 21202726.44 | 32963348.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-24 | 2026-05-25
RR/RDA/16/25/10KM/04/AKK/AMP | RR/RDA/16/25/10KM/04 | Vevinna Boogas Junction Inner Road | Ampara | Ampara | Gama Construction & Consultant pvt Ltd | 15% | 9692957.45 | 14460000 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-07 | 2026-05-08
RR/RDA/16/25/10KM/05/AKK/AMP | RR/RDA/16/25/10KM/05 | Road from Dorapaha Junction to Navagiriya Lake | Ampara | Ampara | Ema Constructions (Pvt) Ltd | 10% | 18058942 | 28554939.58 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-09 | 2026-06-07
RR/RDA/16/25/10KM/07/AKK/AMP | RR/RDA/16/25/10KM/07 | Bedirakka Malgastalawa Road | Ampara | Dehiaattakandiya | Pearl Construction | 0% | 16362791.5 | 28483156.49 | Awarded | Tender Below 50Mn |  |  |  | 2026-03-14 | 2026-05-15
RR/RDA/16/25/10KM/08/AKK/AKK | RR/RDA/16/25/10KM/08 | RDS Road Addalachena 6, 8 | Ampara | Akkaraipattu | MLH & sons Construction | 0% | 18326682.5 | 29731841.59 | Awarded | Tender Below 50Mn |  |  |  | 2026-02-26 | 2026-05-27
RR/RDA/16/25/10KM/11/AKK/AKK | RR/RDA/16/25/10KM/11 | Kalyana Road - Periyanilavanai Vishnu Kovil Road to Maradamuna Mashur Maulana Road | Ampara | Kalmunai | Zaka Engineering Consultancy | 10% | 20596083.2 | 32835450.73 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-08 | 2026-06-06
RR/RDA/16/25/10KM/13/AKK/AKK | RR/RDA/16/25/10KM/13 | Jaica - Tsunami Village Road | Ampara | Akkaraipattu | Gama Construction & Consultant pvt Ltd | 70% | 26167747.32 | 39951889.78 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-15 | 2026-06-13
RR/RDA/15/25/02/EP/BTC | RR/RDA/15/25/02 | Concreting to Samurthi 1st Cross road | Batticaloa | Batticaloa | Kumaran Construction and Civil Works | 20% | 22158474.12 | 42354466.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2025-02-06 | 2026-02-15
RR/RDA/15/25/15/EP/BTC | RR/RDA/15/25/15 | Concrete to the Majma Nagar Mullivattuvan at paper town 210B | Batticaloa | Batticaloa | KMC Construction | 80% | 25270404.71 | 44093282.42 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-15
RR/RDA/15/25/05/EP/BTC | RR/RDA/15/25/05 | Concreting to Mailanthanai Sri Muththumariyamman Main Road | Batticaloa | Batticaloa | Kumaran Construction and Civil Works | 50% | 23225083.2 | 44365292.45 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-15
RR/RDA/15/25/09/EP/BTC | RR/RDA/15/25/09 | Concreting to NHDA Housing Scheme Internal Road 1st 2nd Cross | Batticaloa | Batticaloa | DKJ Construction | 40% | 7972333.63 | 16362900.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-15
RR/RDA/15/25/11/EP/BTC | RR/RDA/15/25/11 | Concreting to Kali Kovil Road | Batticaloa | Batticaloa | Jeezan Trading and Transport | 5% | 14105564 | 27925821.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-08
RR/RDA/15/25/12/EP/BTC | RR/RDA/15/25/12 | Concreting to Muthalaikuda to Munnaikkadu Boundary Road | Batticaloa | Batticaloa | Kumaran Construction and Civil Works | 40% | 26564874.51 | 47720744.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-20 | 2026-02-15
RR/RDA/15/25/13/EP/BTC | RR/RDA/15/25/13 | Concreting to Sangarpuram- Vilavadi | Batticaloa | Batticaloa | Kumaran Construction and Civil Works | 10% | 24189660 | 46948339.52 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-20 | 2026-02-15
RR/RDA/15/25/14/EP/BTC | RR/RDA/15/25/14 | Concreting to Agriculture Road | Batticaloa | Batticaloa | Jeezan Trading and Transport | 60% | 10593750 | 21690291.65 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-08
RR/RDA/15/25/10KM/01/BTC | RR/RDA/15/25/10KM/01 | Sooriya farm Road sathurukondan | Batticaloa | Batticaloa | Ganan Construction | 50% | 20565497.24 | 29978952.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-24 | 2026-10-23
RR/RDA/15/25/10KM/02/BTC | RR/RDA/15/25/10KM/02 | Iruthayapuram west 8th cross | Batticaloa | Batticaloa | Sanju Civil Construction | 30% | 27156544.25 | 37780902.59 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-24 | 2026-10-23
RR/RDA/15/25/10KM/07/BTC | RR/RDA/15/25/10KM/07 | Kanady cross Road to Magalingeshwarar kovil Road | Batticaloa | Batticaloa | Motec Engineering & Construction | 5% | 25946118 | 36198556.07 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-04 | 2026-11-03
RR/RDA/15/25/10KM/08/BTC | RR/RDA/15/25/10KM/08 | Poosakar Road, Kannakipuram, Mahiloor | Batticaloa | Batticaloa | Nathan's Construction | 95% | 27673151 | 40745256.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-24 | 2026-10-23
RR/RDA/17/25/09/EP/TRN | RR/RDA/17/25/09 | School-Galmetiyawa Main Internal Road | Trincomalee | Trincomalee | Zaka Engineering Consultancy | 50% | 53122107.5 | 77200000 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-05-22 | 2026-08-21 | 2026-07-31
RR/RDA/17/25/11/EP/TRN | RR/RDA/17/25/11 | Development of Road from near the Fair | Trincomalee | Trincomalee | MS Construction | 15% | 25280343.6 | 37892493.36 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-04 | 2026-09-03
RR/RDA/17/25/19/EP/TRN | RR/RDA/17/25/19 | Periya Suwami Kovil Road-Concrete | Trincomalee | Trincomalee | Motec Engineering & Construction | 20% | 25774146 | 39914113.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-04 | 2026-09-03
RR/RDA/SP/17/25/03/EP/TRN | RR/RDA/SP/17/25/03 | Hajra Road (Alhira Jalaira Road) | Trincomalee | Trincomalee | STAAR Construction | 40% | 38692742 | 51948669.36 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-05-22 | 2026-08-21
RR/RDA/17/25/10KM/04/EP/TRN | RR/RDA/17/25/10KM/04 | Kajuwaththa gama meda road | Trincomalee | Trincomalee | NMST Construction | 5% | 22770000 | 29466015.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-31 | 2026-10-29
RR/RDA/17/25/10KM/06/EP/TRN | RR/RDA/17/25/10KM/06 | Budu pilima and 4th lane road | Trincomalee | Trincomalee | RS Construction | 15% | 17520285.64 | 28351870.49 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-31 | 2026-10-29
RR/RDA/17/25/10KM/08/EP/TRN | RR/RDA/17/25/10KM/08 | Paththini Amman Kevil road | Trincomalee | Trincomalee | Alpha Engineering Services & Suppliers | 25% | 30365709 | 46089014.73 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-04 | 2026-11-03
RR/RDA/17/25/10KM/09/EP/TRN | RR/RDA/17/25/10KM/09 | Bazar mosque road | Trincomalee | Trincomalee | MTA Construction | 40% | 32616074.7 | 44293054.87 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-04 | 2026-11-03
RR/RDA/20/25/01/NCP/ANP | RR/RDA/20/25/01 | Road from Thambuttegama - Nochchiyagama road to the road near the DIG's office of Thambuthegama Rajanganaya | Anuradhapura | Anuradhapura | Creates Consultant and Construction | 30% | 96940000 | 147079527.92 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-09-03
RR/RDA/20/25/03/NCP/ANP | RR/RDA/20/25/03 | Thalawa - Eppawala margaye kele Amunukola handiyen aramba vee kele amunukola viddiyalayen divena margaya | Anuradhapura | Anuradhapura | Dissanayaka Builders | 40% | 26155768.37 | 41286372.1 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-01-27 | 2026-06-30
RR/RDA/20/25/04/NCP/ANP | RR/RDA/20/25/04 | A - 9 maragayen aramba vee wale kade dakwa margaya | Anuradhapura | Anuradhapura | Dissanayaka Builders | 45% | 27008370.51 | 43911304.25 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-01-27 | 2026-06-15
RR/RDA/20/25/06/NCP/ANP | RR/RDA/20/25/06 | Ududumbara boogas handiye sita sarakkugala pasal handiya dakwa margaya | Anuradhapura | Anuradhapura | Dissanayaka Builders | 0% | 26692661.01 | 44183866.35 | Awarded | Tender Below 50Mn |  |  |  | 2025-11-04 | 2026-01-27
RR/RDA/20/25/11/NCP/ANP | RR/RDA/20/25/11 | Palayakulama sita halmillakulama dakwa margaya | Anuradhapura | Anuradhapura | Dissanayaka Builders | 75% | 20887268.2 | 33233870.01 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-01-27 | 2026-05-30
RR/RDA/20/25/16/NCP/ANP | RR/RDA/20/25/16 | Hiriwadunna handiye sita idigaswewa pansal handiya dakwa margaya | Anuradhapura | Maradankadawala | Sun Constructions (Pvt) Ltd. | 80% | 33000000 | 59684748.55 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-04 | 2026-05-25
RR/RDA/20/25/18/NCP/ANP | RR/RDA/20/25/18 | Pahala Talawa road of Thalawa Andarawewa road | Anuradhapura | Anuradhapura | HPS Construction | 80% | 32443580.5 | 46999616.7 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-07 | 2026-06-30
RR/RDA/20/25/26/NCP/ANP | RR/RDA/20/25/26 | Development of IV lane from Nuwara Road to Mihinthalaya Road | Anuradhapura | Anuradhapura | Priyantha Civil Engineering | 6% | 29650453.29 | 38283840.94 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-02
RR/RDA/20/25/28/NCP/ANP | RR/RDA/20/25/28 | Development of Rathnayake Mawatha | Anuradhapura | Anuradhapura | Priyantha Civil Engineering | 5% | 23041750.8 | 30142796.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-02-11
RR/RDA/20/25/29/NCP/ANP | RR/RDA/20/25/29 | Development of the road from Udugama Colony rural road near the A9 road to the front of Mr. Somaratne Senanayake's house | Anuradhapura | Maradankadawala | Priyantha Civil Engineering | 0% | 27986392.06 | 32982943.17 | Awarded | Tender Below 50Mn |  |  |  | 2026-08-10 | 2026-11-02
| RR/RDA/20/25/53 | Development of road from Sripura main road to 38 Kolaniya Cemetery | Anuradhapura | Medawachchiya | NMST Contractor | 2% | 27971333.13 | 33546861.12 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-30 | 2026-10-22
| RR/RDA/20/25/54 | Development of road from Wahalkada D6 to Thalapakattialam on Punchimudagama road | Anuradhapura | Medawachchiya | Priyantha Civil Engineering | 5% | 33242915.64 | 40137233.68 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-02
| RR/RDA/20/25/55 | Development of first phase of road from Punewa to Warakwewa | Anuradhapura | Medawachchiya | RSW Engineering | 25% | 29762232.5 | 34843454.4 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-29 | 2026-10-21
| RR/RDA/20/25/56 | Development of the road from Punewa Junction to Kudahalmillewa Lake | Anuradhapura | Medawachchiya | Priyantha Civil Engineering | 25% | 28506545 | 33620055.04 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-02
| RR/RDA/20/25/57 | Development of the road from near Ikirigollawa Muslim Maha Vidyalaya to Ratmalgahawewa main road from near Ikirigollawa dam to Ratmalgahawa road | Anuradhapura | Medawachchiya | WGL Holdings | 30% | 10767548 | 14249058.84 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-02
| RR/RDA/20/25/59 | From Makicchawa Junction to Temple (to Kulumiwakada Junction) | Anuradhapura | Medawachchiya | Priyantha Civil Engineering | 35% | 29006146.8 | 37056005 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-02
RR/RDA/21/25/03/NCP/POL | RR/RDA/21/25/03 | Mahasenpura pradeepika kadaya asala sita Katukeliyawa dakwa margaya Carpart kireema | Polonnaruwa | Habarana | Nadun Construction (Pvt) Ltd | 80% | 33480137.33 | 53473343.43 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-10 | 2026-03-11 | 2026-04-10
RR/RDA/21/25/17/NCP/POL | RR/RDA/21/25/26 | Development of the road from Kaduruwela Muslim Kolaniya road to Pachcha Palliya | Polonnaruwa | Polonnaruwa | Central Engineering Services Pvt Ltd. (CESL) | 80% | 53880000 | 75598504.72 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-05-25 | 2026-08-24 | 2026-10-31
RR/RDA/21/25/17/NCP/POL | RR/RDA/21/25/27 | Development of 1 canal Road from Kadurwela Muslim Kolaniya Road to Parakum Mawatha | Polonnaruwa | Polonnaruwa | Nadun Construction (Pvt) Ltd | 45% | 54640000 | 62351983.93 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-07-02 | 2026-10-01
RR/RDA/18/25/01/NWP/KRG | RR/RDA/18/25/01 | Development of Egodagama Talakolawewa road | Kurunegala | Maho | Sri Ram Constructions | 60% | 98323766.14 | 156184445.89 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-08 | 2026-05-06 | 2026-07-09
RR/RDA/18/25/04/NWP/KRG | RR/RDA/18/25/04 | The road from Hunugallewa road junction to Madadenigama Hunugallewa Mahamaruwa Beligahaya to Mee Oya bridge | Kurunegala | Maho | Shanho Enterprises Pvt Ltd. | 40% | 59066766.74 | 85865152.06 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-09 | 2026-06-09 | 2026-06-09
RR/RDA/18/25/07/NWP/KRG | RR/RDA/18/25/07 | Road from Moragolla Junction to Nabadewa Girilla Carpet Road via Kirinda | Kurunegala | Maho | Jayasinghe Constructions (Pvt) Ltd. | 75% | 59247280.29 | 79393864.19 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-09 | 2026-05-12 | 2026-06-12
RR/RDA/18/25/09/NWP/KRG | RR/RDA/18/25/09 | Paving the road from Pahala Galapitiyagama to Tharanagolla Sports Ground | Kurunegala | Maho | Senerath Engineering (pvt) Ltd | 0% | 70405428.6 | 81982091.15 | Awarded | Tender Above 50Mn |  |  |  | 2025-12-03 | 2026-03-03 | 2026-03-03
RR/RDA/18/25/11/NWP/KRG | RR/RDA/18/25/11 | Development of road from Dambulu Road to Havanathenna via Ehelagollaya | Kurunegala | Kurunegala | Shanho Enterprises Pvt Ltd. | 65% | 46193949.68 | 64750199.52 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-07-01 | 2026-08-01
RR/RDA/18/25/22/NWP/KRG | RR/RDA/18/25/22 | Paving of culverts and sidewalls at the necessary places on the road from near Moragane Samiti Hall to Siyambalaweva via Galkadulla. | Kurunegala | Kuliyapitiya | Jayasinghe Constructions (Pvt) Ltd. | 65% | 67074479.55 | 77881819.09 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-03 | 2026-06-04 | 2026-07-04
RR/RDA/18/25/135/NWP/KRG | RR/RDA/18/25/135 | Kelegedara Gamameda Road (CTB Basaya Dawanaya wana) Kavudumunna, Kunumade, Hungan pitiya haraha diwena Margaya Kapat Kirima | Kurunegala | Kurunegala | Jayasinghe Contractors (Pvt) Ltd. | 20% | 41750386.7 | 55779764.12 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-05-20 | 2026-05-20
RR/RDA/18/25/137/NWP/KRG | RR/RDA/18/25/137 | Damunugolla Sita Kobbewehera Handiya Dakwa Margaya Kapat Kirima | Kurunegala | Kurunegala | W P J Engineering(Pvt)Ltd | 45% | 18425029.46 | 23865719.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-07 | 2026-04-06 | 2026-06-06
RR/RDA/18/25/138/NWP/KRG | RR/RDA/18/25/138 | Pudukkulama Bogas Handiye sita Keppitiya haraha Thihawa Dakwa Margaya Kapat Kirima | Kurunegala | Kurunegala | W P J Engineering(Pvt)Ltd | 20% | 30650394.06 | 39359193.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-07 | 2026-04-07 | 2026-06-07
RR/RDA/18/25/139/NWP/KRG | RR/RDA/18/25/139 | Akkara Panaha Mansandiye Sita Walahamulla Dakwa Margaya | Kurunegala | Kurunegala | Jayawansa Construction (PVT) Ltd | 90% | 28112995.75 | 41102824.35 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-17 | 2026-05-18 | 2026-06-18
| RR/RDA/18/25/308 | Wijekoon Mawatha near Narammala Bus Stand and Hospital Mawatha from Peralaswella | Kurunegala | Kuliyapitiya | Thushara roofing (pvt) ltd | 65% | 10696008.28 | 11985499.69 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-04 | 2026-08-02
RR/RDA/19/25/01/NWP/PUT | RR/RDA/19/25/01 | Development of carpeting the Gammedda road up to Anathapara. | Puttalam | Puttalam | Chandana Construction | 65% | 27734432.55 | 24961884.73 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-21 | 2025-12-20 | 2026-07-19
RR/RDA/19/25/04/NWP/PUT | RR/RDA/19/25/04 | Carpeting of green light carpeted road from Bogus Junction (80 acres). | Puttalam | Chilaw | Sri Ram Constructions | 65% | 34055720.05 | 59154724.51 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-09 | 2026-03-09 | 2026-06-09
RR/RDA/19/25/05/NWP/PUT | RR/RDA/19/25/05 | Development of the road from near Mr. Chaminda's house to Boga Pathaha | Puttalam | Puttalam | Sampath Contractors | 65% | 36592843.95 | 60367316.08 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-04 | 2026-07-04
RR/RDA/19/25/08/NWP/PUT | RR/RDA/19/25/08 | Carpeting of Velasia Main Road from Madurankuliya. | Puttalam | Puttalam | Sri Ram Constructions | 70% | 39584083.5 | 61899364.5 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-04-04 | 2026-05-04
RR/RDA/19/25/27/NWP/PUT | RR/RDA/19/25/27 | The entrance to the Medical Officer's Office in the Galahitiyawa Grama Niladhari Division | Puttalam | Chilaw | Omega Construction (Pvt) Ltd | 60% | 38495776 | 49714778.94 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-03 | 2026-06-03
RR/RDA/19/25/30/NWP/PUT | RR/RDA/19/25/30 | Development of carpeting from Mihirajthotupola to Serakkuliya 1 on the Serakkuliya main road | Puttalam | Puttalam | Omega Construction (Pvt) Ltd | 70% | 38494009.5 | 45465357.54 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-12 | 2026-04-12 | 2026-06-12
RR/RDA/19/25/31/NWP/PUT | RR/RDA/19/25/31 | Development of carpeting from the point where carpeting has stopped on the Tammana main road | Puttalam | Puttalam | Sampath Construction | 50% | 26013841.83 | 39960885.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-12 | 2026-05-13 | 2026-05-13
RR/RDA/19/25/32/NWP/PUT | RR/RDA/19/25/32 | Development of the Bammeyaya Road | Puttalam | Puttalam | Jayawardana Constructions (Pvt) Ltd. | 50% | 10904293.4 | 17431257.91 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-12 | 2026-05-12 | 2026-06-12
RR/RDA/19/25/33/NWP/PUT | RR/RDA/19/25/33 | Development of the road from near the Sugatarama Temple, Periyakulam to Thalgaswewa | Puttalam | Puttalam | Jayawardana Constructions (Pvt) Ltd. | 45% | 24440875.25 | 38370082.14 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-12 | 2026-04-12 | 2026-06-12
RR/RDA/19/25/34/NWP/PUT | RR/RDA/19/25/34 | Carpeting & Development of Bodhirajapura 4th Lane | Puttalam | Puttalam | Sampath Construction | 70% | 12568847.5 | 19966435.66 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-12 | 2026-05-12 | 2026-05-13
RR/RDA/19/25/37/NWP/PUT | RR/RDA/19/25/37 | Lawyer Wijayananda's House Road | Puttalam | Chilaw | Ponnamperuma Suppliers | 70% | 7763919.68 | 9913614.44 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-13 | 2026-04-14 | 2026-06-13
RR/RDA/19/25/38/NWP/PUT | RR/RDA/19/25/38 | North Dummaladeniya Cross Road | Puttalam | Chilaw | Ponnamperuma Suppliers | 90% | 10005001.78 | 11621041.2 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-14 | 2026-04-14 | 2026-04-14
RR/RDA/19/25/39/NWP/PUT | RR/RDA/19/25/39 | Renovation of Khemananda Road | Puttalam |  | SriLak Import and Export Company | 95% | 19114271.45 | 22000226.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-19 | 2026-04-19 | 2026-04-19
| RR/RDA/19/25/40 | Development of the road from Madurankuliya to Velasiya College | Puttalam | Puttalam | Sampath Construction | 30% | 55254878 | 90437412.35 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-05-21
| RR/RDA/19/25/91 | Development of Fenando Road - Picchawala Road | Puttalam | Chilaw | Dilini Builders (PVT) LTD | 0% | 26046308.34 | 27030199.65 | Awarded | Tender Below 50Mn |  |  |  | 2026-05-20 | 2026-08-17
RR/RDA/10/25/06/NP/JFN | RR/RDA/10/25/06 | Renovation of West beach Road | Jaffna | Jaffna | Sun Constructions (Pvt) Ltd. | 10% | 83618425 | 91211155.29 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-04-18 | 2026-07-31
RR/RDA/10/25/14/NP/JFN | RR/RDA/10/25/14 | Pankuru Veethy | Jaffna | Jaffna | Thaaru Construction | 60% | 32829728.8 | 47295898.62 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-05-26 | 2026-05-26
RR/RDA/10/25/18/NP/JFN | RR/RDA/10/25/18 | Atchuvely Industrial Road | Jaffna | Jaffna | Sun Constructions (Pvt) Ltd. | 70% | 72500000 | 101707442.89 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-03 | 2026-04-04 | 2026-05-31
RR/RDA/10/25/22/NP/JFN | RR/RDA/10/25/22 | Anaivilunthan Sudalai Road | Jaffna | Point Pedro | Yaso Engineering | 65% | 48082026.3 | 61126170.56 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-04-03 | 2026-06-03
RR/RDA/10/25/25/NP/JFN | RR/RDA/10/25/25 | Palaiya Vaikal Veeethy | Jaffna | Point Pedro | Sun Constructions (Pvt) Ltd. | 50% | 54450000 | 79703717.02 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-02 | 2026-06-15
RR/RDA/12/25/01/NP/VVN | RR/RDA/12/25/01 | Thiruchchenthooran mill road NVSTE541 | Vavuniya | Vavuniya | TMC Constructions | 0% | 53290000 | 100688815.19 | Awarded | Tender Above 50Mn |  |  |  | 2026-07-01 | 2026-09-29
RR/RDA/12/25/03/NP/VVN | RR/RDA/12/25/03 | Puthiya manipuram, main road (NVSTE481) | Vavuniya | Vavuniya | Yaso Engineering | 35% | 32481108 | 41435979.42 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13
RR/RDA/12/25/04/NP/VVN | RR/RDA/12/25/04 | Suntharapuram main road | Vavuniya | Vavuniya | Sun Constructions (Pvt) Ltd. | 35% | 162703000 | 71964095.93 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-03
RR/RDA/12/25/17/NP/VVN | RR/RDA/12/25/17 | Lyca village enterance Road | Vavuniya | Vavuniya | Sun Constructions (Pvt) Ltd. | 35% | 0 | 54064384.24 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-03
RR/RDA/12/25/22/NP/VVN | RR/RDA/12/25/22 | Mannankerny road | Vavuniya | Vavuniya | Sun Constructions (Pvt) Ltd. | 50% | 0 | 51515196.2 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-03
RR/RDA/12/25/52/NP/VVN | RR/RDA/12/25/52 | Menanager Malakattu Kalkuwari Road | Vavuniya | Vavuniya | Sun Constructions (Pvt) Ltd. | 65% | 0 | 54861523.89 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-03
RR/RDA/12/25/07/NP/VVN | RR/RDA/12/25/07 | Tharanikulam main road | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 70% | 20876280.7 | 30580213.01 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/10/NP/VVN | RR/RDA/12/25/10 | Achchipuram amman temble road | Vavuniya | Vavuniya | Ancheneya Constructions | 70% | 19430799.3 | 28181354.24 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/12/NP/VVN | RR/RDA/12/25/12 | Nanthimiththiragama 1st | Vavuniya | Vavuniya | Ancheneya Constructions | 5% | 24583111.3 | 30752460 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-05-22
RR/RDA/12/25/13/NP/VVN | RR/RDA/12/25/13 | Nanthimiththiragama 2nd | Vavuniya | Vavuniya | Ancheneya Constructions | 5% | 24829841.3 | 31291948.01 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-04-22
RR/RDA/12/25/14/NP/VVN | RR/RDA/12/25/14 | Nanthimiththiragama 4th | Vavuniya | Vavuniya | Ancheneya Constructions | 5% | 25113641.3 | 30939872.36 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-04-22
RR/RDA/12/25/18/NP/VVN | RR/RDA/12/25/18 | Nedunkerny North sandankulam Road | Vavuniya | Vavuniya | Yaso Engineering | 35% | 32829160.1 | 46839314.91 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-12
RR/RDA/12/25/19/NP/VVN | RR/RDA/12/25/19 | Senaipilavu Road | Vavuniya | Vavuniya | Yaso Engineering | 70% | 32576225 | 43285227.82 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-12
RR/RDA/12/25/20/NP/VVN | RR/RDA/12/25/20 | Puthiyakudiyiruppu parasankulam road | Vavuniya | Vavuniya | Bapithan Construction | 70% | 23259239.3 | 34966229.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/21/NP/VVN | RR/RDA/12/25/21 | Bagaswewa 01st 22nd lane | Vavuniya | Vavuniya | Bapithan Construction | 35% | 22749983.3 | 33747516.65 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/24/NP/VVN | RR/RDA/12/25/24 | Kanagarayankulam puthuvilankulam road (NVVNE073) | Vavuniya | Vavuniya | Bapithan Construction | 70% | 31165786.3 | 46468981.72 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13
RR/RDA/12/25/25/NP/VVN | RR/RDA/12/25/25 | 2nd cross Lane Ginigathhena | Vavuniya | Vavuniya | Nimna Holdings (Pvt) Ltd | 70% | 27770291 | 40686140.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-02-21
RR/RDA/12/25/27/NP/VVN | RR/RDA/12/25/27 | From Acre 400 7th Lane to cross end of the 2nd internal road close to Andarawewa | Vavuniya | Vavuniya | Ranasinghe Construction | 30% | 46360659.24 | 57948785.02 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-03-03
RR/RDA/12/25/28/NP/VVN | RR/RDA/12/25/28 | From Janaudanagama 2nd internal road to end of the free school | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 35% | 26569012.25 | 37396800.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/29/NP/VVN | RR/RDA/12/25/29 | Kalasiyambalawa Road | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 50% | 13504281.45 | 19583811.27 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13
RR/RDA/12/25/31/NP/VVN | RR/RDA/12/25/31 | Mahakachchakodiya to Ettambagaskada | Vavuniya | Vavuniya | Yansika Construction | 30% | 45254190.85 | 59974624.42 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-01-20
RR/RDA/12/25/35/NP/VVN | RR/RDA/12/25/35 | Awusadapitiya Pubudugama Road | Vavuniya | Vavuniya | Nimna Holdings (Pvt) Ltd | 70% | 32504637.43 | 46347432.25 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-02-21
RR/RDA/12/25/38/NP/VVN | RR/RDA/12/25/38 | Salalinigama 11 lane | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 50% | 30830906.7 | 40853027.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/40/NP/VVN | RR/RDA/12/25/40 | Halabagaswewa | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 5% | 25032191.25 | 36283467.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/43/NP/VVN | RR/RDA/12/25/43 | Pavatkulam tack 5 vaarikuttiyoor | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 70% | 17351705.25 | 25717072.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/48/NP/VVN | RR/RDA/12/25/48 | Mukaththankulam 7th lane (NVVPE173) | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 70% | 18900081.2 | 28294497.45 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/51/NP/VVN | RR/RDA/12/25/51 | Adappankulam aladi road | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 70% | 13383862.25 | 19573472.29 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/54/NP/VVN | RR/RDA/12/25/54 | Nikawewa Right Village Road | Vavuniya | Vavuniya | Yansika Construction | 70% | 17143053.95 | 22922029.4 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/60/NP/VVN | RR/RDA/12/25/60 | Salalinigama lane 12 | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 15% | 23397220 | 33827661.22 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-03 | 2026-07-03
RR/RDA/12/25/62/NP/VVN | RR/RDA/12/25/62 | Periyavilathikulam | Vavuniya | Vavuniya | Omega Construction (Pvt) Ltd | 35% | 16916712.5 | 23338487.33 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-03 | 2026-07-03
RR/RDA/12/25/63/NP/VVN | RR/RDA/12/25/63 | 1st Cross Street Alakarai Road | Vavuniya | Vavuniya | North Construction | 30% | 38912500 | 55600429.77 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-05-21
RR/RDA/12/25/64/NP/VVN | RR/RDA/12/25/64 | Nedunkulama | Vavuniya | Vavuniya | Arul Selvi Construction and Hardware | 70% | 15902966.56 | 22278087.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-03 | 2026-07-03
RR/RDA/13/25/01/NP/MUL | RR/RDA/13/25/01 | Akkaraiveli Paraiyanaru ( Vilaththiyad) Road Package 1 | Mullaitivu | Mullaitivu | Sun Constructions (Pvt) Ltd. | 0% | 145000000 | 188808095.02 | Awarded | Tender Above 50Mn |  |  |  | 2025-12-02 | 2026-03-02
RR/RDA/13/25/03/NP/MUL | RR/RDA/13/25/03 | Navatkadu Road | Mullaitivu | Mullaitivu | TMC Constructions | 60% | 50363687 | 77969519 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-01 | 2026-06-06
RR/RDA/13/25/06/NP/MUL | RR/RDA/13/25/06 | Pandaravanniyan Silaiyadi Road | Mullaitivu | Mullaitivu | Sun Constructions (Pvt) Ltd. | 40% | 83700000 | 113438730.78 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-26 | 2026-03-26
RR/RDA/13/25/07/NP/MUL | RR/RDA/13/25/07 | Kanagarayankulam District Boundary Road (Old Kandy road) | Mullaitivu | Mullaitivu | Sun Constructions (Pvt) Ltd. | 60% | 159972500 | 220671169.9 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-26 | 2026-03-26 | 2026-06-12
RR/RDA/13/25/08/NP/MUL | RR/RDA/13/25/08 | Kumulamunai Akkarayan road | Mullaitivu | Mullaitivu | Nimna Holdings (Pvt) Ltd | 70% | 148861042 | 198505802.7 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-01 | 2026-06-20
RR/RDA/13/25/10/NP/MUL | RR/RDA/13/25/10 | Pandiyankulam Neddankandal Road | Mullaitivu | Mullaitivu | Nimna Holdings (Pvt) Ltd | 70% | 144696282.5 | 191627958.51 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-01 | 2026-06-10
RR/RDA/13/25/11/NP/MUL | RR/RDA/13/25/11 | Ethawetuvuwewa to Sampathnuwara | Mullaitivu | Mullaitivu | Nimna Holdings (Pvt) Ltd | 30% | 110422944.5 | 141810206.62 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-22 | 2026-06-22
RR/RDA/11/25/01/NP/MNR | RR/RDA/11/25/01 | Mahilankulam Pallamadhu road | Mannar | Mannar | George Steuart Engineering (Pvt)Ltd | 50% | 189602588.3 | 274228723.54 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-26 | 2026-05-25
RR/RDA/11/25/02/NP/MNR | RR/RDA/11/25/02 | Piramanayankulam Parappukadanthan road | Mannar | Mannar | George Steuart Engineering (Pvt)Ltd | 55% | 169538631.82 | 244135763.06 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-26 | 2026-05-25
RR/RDA/11/25/04/NP/MNR | RR/RDA/11/25/04 | Tharavankottai to Keeri Main Road | Mannar | Mannar | VN Construction JV | 60% | 146489579.5 | 76333504.2 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-04
RR/RDA/11/25/07/NP/MNR | RR/RDA/11/25/07 | Avithappar Panimayam Internal Road with Culvert - Pesalai | Mannar | Mannar | VN Construction JV | 70% | 0 | 85087335.02 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-04
RR/RDA/11/25/11/NP/MNR | RR/RDA/11/25/11 | Eruvittan - Vellalakaddu Road | Mannar | Mannar | VN Construction JV | 5% | 0 | 57826727.83 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-04
RR/RDA/11/25/05/NP/MNR | RR/RDA/11/25/05 | Konnayan Kudiyiruppu Internal Main Road | Mannar | Mannar | Sun Constructions (Pvt) Ltd. | 5% | 90000000 | 135947165.98 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-08 | 2026-05-09
RR/RDA/11/25/09/NP/MNR | RR/RDA/11/25/09 | Renovation of Mathirikiramam internal Road Naruvilikulam | Mannar | Mannar | Abdul Cader Constructions | 70% | 28422878 | 40820067.58 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-03-11
RR/RDA/11/25/16/NP/MNR | RR/RDA/11/25/16 | P.P.Potkerny Scheme Internal Road 1 | Mannar | Mannar | Abdul Cader Constructions | 70% | 14295963 | 20672459.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-02
RR/RDA/11/25/18/NP/MNR | RR/RDA/11/25/18 | Akaththimurippu Internal Road 3 | Mannar | Mannar | Abdul Cader Constructions | 70% | 15815393 | 23278986.71 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-02
RR/RDA/14/25/06/NP/KLN | RR/RDA/14/25/06 | Skanthapuram Kannan Temple road | Kilinochchi | Kilinochchi | Sun Constructions (Pvt) Ltd. | 35% | 138750000 | 214117844.07 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-03
RR/RDA/14/25/08/NP/KLN | RR/RDA/14/25/08 | Kalmadu 7th unit 3rd lane | Kilinochchi | Kilinochchi | Kanola Constructions & Engineering (Pvt) Ltd | 20% | 58116410 | 92284361.31 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-03
RR/RDA/14/25/09/NP/KLN | RR/RDA/14/25/09 | Neliyai Amman kovil road | Kilinochchi | Kilinochchi | Kanola Constructions & Engineering (Pvt) Ltd | 0% | 113238042.5 | 182796432.72 | Awarded | Tender Above 50Mn |  |  |  | 2025-12-10 | 2026-03-10
RR/RDA/10/25/24/NP/KLN | RR/RDA/10/25/24 | Kevil Nithtiyaveddai Road 2.150 | Kilinochchi | Kilinochchi | Kanola Constructions & Engineering (Pvt) Ltd | 0% | 67998480 | 112111761.11 | Awarded | Tender Above 50Mn |  |  |  | 2025-12-10 | 2026-03-10
RR/RDA/25/24/01/SBP/RTP | RR/RDA/25/24/01 | From Delgas Junction To Vilehena Road | Ratnapura | Ratnapura | Siri Construction | 90% | 30346327.41 | 43303726.54 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15
RR/RDA/25/24/02/SBP/RTP | RR/RDA/25/24/02 | Thundola Varathenna Road | Ratnapura | Embilipitiya | Siri Construction | 35% | 123540895.5 | 122516687.81 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-05-02 | 2026-04-27
RR/RDA/25/24/03/SBP/RTP | RR/RDA/25/24/03 | From Thunaghahena To Temple Road | Ratnapura | Ratnapura | Siri Construction | 95% | 20065425.82 | 27753891.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15
RR/RDA/25/24/10/SBP/RTP | RR/RDA/25/24/10 | From Deniya kade Market to Henyaya Road Via Keenagahaella Road | Ratnapura | Pelmadulla | Sam Dam | 95% | 31673916.45 | 50516461.34 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-27
RR/RDA/24/25/21/SBP/RTP | RR/RDA/24/25/21 | Sudagala Grama Seva Division, From Sudagala to Tunudola Road up the mountain to near the cooperative | Ratnapura | Ratnapura | DKS Construction | 0% | 35222472.34 | 42448062.24 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-15 | 2026-10-13
RR/RDA/24/25/34/SBP/RTP | RR/RDA/24/25/34 | Matuwagala Mudun Kotu Road | Ratnapura | Ratnapura | DKS Construction | 0% | 0 | 33238726.51 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-15 | 2026-10-13
RR/RDA/25/25/02/SBP/KGL | RR/RDA/25/25/02 | Elagapitiya Colany Road From Debathgama Pallebage to Tea Shakthi Praja Shalawa | Kegalle | Kegalle | EHL Constructions | 85% | 36210751.61 | 52222845.54 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-03 | 2026-05-04
RR/RDA/25/25/03/SBP/KGL | RR/RDA/25/25/03 | From Kehelpannala Junction to Pahala Kabawita Road | Kegalle | Kegalle | SF Constructions | 95% | 71786959.2 | 96478103.45 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-30
RR/RDA/25/25/15/SBP/KGL | RR/RDA/25/25/15 | Moraliya Gagaboda Road | Kegalle | Ruwanwella | DHP Construction | 90% | 38093328.62 | 48285852.39 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-03 | 2026-02-01
RR/RDA/25/25/20/SBP/KGL | RR/RDA/25/25/20 | Neluwakkana gama meda Road | Kegalle | Ruwanwella | Loshitha Construction | 95% | 23823804.13 | 33221060.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-20 | 2026-02-18
RR/RDA/25/25/28/SBP/KGL | RR/RDA/25/25/28 | Naagas thenna Road | Kegalle | Ruwanwella | Jayasinghe Contractors (Pvt) Ltd. | 90% | 102000742.36 | 103886540.99 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-11 | 2026-08-12
RR/RDA/25/25/34/SBP/KGL | RR/RDA/25/25/34 | Road Connecting Ihala Palampitiya and Pahala Palampitiya | Kegalle | Ruwanwella | DKS Nishantha Construction | 0% | 26331747.62 | 36648120.48 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-24 | 2026-10-22
RR/RDA/25/25/35/SBP/KGL | RR/RDA/25/25/35 | Kudadeniya Adurapola Watta Road | Kegalle | Ruwanwella | TMT Construction | 60% | 29362927.93 | 41661137.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-02
RR/RDA/25/25/38/SBP/KGL | RR/RDA/25/25/38 | Development of the road near the closed tea factory on Edurapola Watta main road | Kegalle | Ruwanwella | TMT Construction | 95% | 22209331.1 | 30599205.16 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-04
RR/RDA/25/25/39/SBP/KGL | RR/RDA/25/25/39 | Development of Gatayamulla Jagatpura Pannala Rasnadeniya road | Kegalle | Ruwanwella | Samindra Construction | 95% | 31491651.4 | 32775992.83 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-02 | 2026-08-31 | 2026-08-31
RR/RDA/25/25/40/SBP/KGL | RR/RDA/25/25/40 | Kabagamuwa 17 Acres Road Development | Kegalle | Ruwanwella | TMT Construction | 95% | 14823379.41 | 18604688.76 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-28 | 2026-05-28
RR/RDA/07/25/02/SP/GAL | RR/RDA/07/25/02 | Delgahabedda-Kirimatiya Margaya | Galle | Galle | Dissanayaka Builders | 93% | 26404581.16 | 50069275.91 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-31
RR/RDA/07/25/05/SP/GAL | RR/RDA/07/25/05 | Atawalawatta Sri Rewatha Viduhala Idiripita Margaya | Galle | Galle | Dissanayaka Builders | 95% | 25809376.97 | 45727567.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-28
RR/RDA/07/25/09/SP/GAL | RR/RDA/07/25/09 | Panwila Hena Pradhana Margaya Lalith Mahathage Niwasa Asala Sita Manjula Jayaweera Mahathage Niwasa Dakwa Margaya | Galle | Hiniduma | DGSD Construction | 98% | 28039359.88 | 42959652.18 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-03-31
RR/RDA/07/25/17/SP/GAL | RR/RDA/07/25/17 | Dasa Kadaya Asala sita Jack Fruit Ceylon (Pvt) ayathanaya dakwa Margaya 1 Km carpert kirima | Galle | Galle | P.H. Engineering Construction (Pvt) Ltd | 47% | 20798250 | 33516218.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/25/19/SP/GAL | RR/RDA/07/25/19 | SuriEla Margaya | Galle | Galle | A.D. Herath Engineering | 96% | 14387747 | 18573267.25 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2026-01-08 | 2026-02-27
RR/RDA/08/25/18/SP/MTR | RR/RDA/08/25/18 | Dekatukella Margaya Pethibemma sahithawa Sanwardanaya kirima | Matara | Matara | Dashodhaya (Pvt)Ltd | 0% | 4080866.9 | 6117703.11 | Awarded | Tender Below 50Mn |  |  |  | 2025-10-09 | 2026-01-08 | 2025-12-16
RR/RDA/09/25/08/SP/HMB | RR/RDA/09/25/08 | Carpeting Pissubedda Medagamgoda road | Hambantota | Tangalle | Samarasinghe Construction(Pvt)Ltd | 98% | 28923336.75 | 46881232.95 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-20 | 2026-06-19
RR/RDA/09/25/09/SP/HMB | RR/RDA/09/25/09 | Development of the road in front of Godawela School to Ambussa Wela | Hambantota | Tangalle | A.T.L. Construction | 60% | 34500631 | 47452621.54 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-07 | 2026-07-23 | 2026-08-31
RR/RDA/09/25/11/SP/HMB | RR/RDA/09/25/11 | Development of Walasmulla Daluwakgoda School Road | Hambantota | Tangalle | Samarasinghe Construction(Pvt)Ltd | 20% | 34814777.8 | 48463720.72 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-04 | 2026-09-03 | 2026-09-03
RR/RDA/09/25/13/SP/HMB | RR/RDA/09/25/13 | Development of the road from Puak Dandawa near Aligerappa house through Weerasijahagoda to Satinamaluwa Kapuduarawatta field. | Hambantota | Tangalle | A.T.L. Construction | 60% | 23847807.5 | 30673898.39 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-06 | 2026-07-22 | 2026-08-31
RR/RDA/22/25/07/UP/BDL | RR/RDA/22/25/07 | Tharuna Govipola Margaye ithiri Kotasa Sanwardanaya Kirieema | Badulla | Bandarawela | Samadhi Construction | 0% | 13290035.01 | 15552666.77 | Awarded | Tender Below 50Mn |  |  |  | 2025-11-14 | 2026-02-13
RR/RDA/22/25/22/UP/BDL | RR/RDA/22/25/22 | Achchupatti Margaya | Badulla | Badulla | Priyankara Industries and Contractors | 20% | 25269262.7 | 30435860.35 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-06 | 2026-02-05
RR/RDA/01/25/14/WP/COL | RR/RDA/01/25/14 | Development of the section from Arangala Bridge to Mihindu Mawatha in Malabe West Division | Colombo | Colombo | W.A. Perera & Company (Pvt) Ltd. | 68% | 33591596.5 | 51359519.36 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-10 | 2026-05-12
RR/RDA/01/25/19WP/COL | RR/RDA/01/25/19 | Puwakpitiya Dharmalapala Mawatha Main Road Development of the road from High Level Road to Elstonwatte Volleyball Court | Colombo | Avissawella | Asela Construction | 90% | 9189060 | 11872168.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-13 | 2026-05-15
RR/RDA/01/25/26/WP/COL | RR/RDA/01/25/26 | Boraluwathenna Pahala Uda Road | Colombo | Avissawella | Next Engineering Services (PVT) LTD | 5% | 21870721.4 | 27759276.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-28 | 2026-05-29
RR/RDA/01/25/30/WP/COL | RR/RDA/01/25/30 | Development of the road from near the transformer near Seebara Kade, Boralugoda to the Jayanthi Road | Colombo | Colombo | Asset Engineering (Pvt)LTD | 0% | 21619184.95 | 22641802.22 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-30 | 2026-08-29
RR/RDA/02/25/03/WP/GMP | RR/RDA/02/25/03 | Development of De silva road beginning from Angurukaramulla temble road to Negombo Colombo road | Gampaha | Negombo | Dilini Builders (PVT) LTD | 0% | 5430100 | 6886574.13 | Awarded | Tender Below 50Mn |  |  |  | 2026-06-29 | 2026-09-28
RR/RDA/02/25/08 | RR/RDA/02/25/08 | Carpeting of the road from near the Buddha Temple towards the Lindara Temple on the Neligama Guru Godella Road started from Halugama Dharmapala Colledge in the Lindara Grama Niladhari Division of the Mirigama Divisional Secretariat. | Gampaha | Nittambuwa | Wijerathna Construction | 20% | 44980000 | 69742766.87 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-07 | 2026-06-05
| RR/RDA/02/25/10 | The road from Thaladuwa Road near Negombo Bus Stand, passing Jude Church, to the cemetery | Gampaha | Negombo | Dilini Builders (PVT) LTD | 0% | 35997890 | 43987022.27 | Awarded | Tender Below 50Mn |  |  |  | 2026-05-13 | 2026-08-12
| RR/RDA/02/25/11 | Road from Pinnawatta Junction to Mr. Sandaruwan's shop on the Hapitiya entrance road | Gampaha | Nittambuwa | Jeyanthan Construction | 0% | 15498360 | 21828855.77 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-21 | 2026-07-21
| RR/RDA/02/25/15 | Udupila South Dolewatta | Gampaha | Gampaha | Creates Consultant and Construction | 0% | 7423117.7 | 8968820.62 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-15 | 2026-07-14
RR/RDA/02/25/18/WP/GAM | RR/RDA/02/25/18 | Peliyagoda Naranminiya Road | Gampaha | Gampaha | Ceylux Civil engineering (Pvt) Ltd | 0% | 19082810 | 24821169.03 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-26 | 2026-10-20
| RR/RDA/02/25/19 | 3 A road carpeted development near the Japanese Montessori at the junction of the North Kadirana Division. | Gampaha | Negombo | Jeyanthan Construction | 0% | 15141484.5 | 21486157.55 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-21 | 2026-07-21
| RR/RDA/02/25/22 | 241 B Near Weliweriya North Suruwama Junction to Weliweriya Town | Gampaha | Gampaha | Yagoda Construction | 0% | 11473274.8 | 12991931.82 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-29 | 2026-10-29
| RR/RDA/02/25/24 | Near Urapana Sisira Coir Mill to Hapugahagama Co-operative | Gampaha | Negombo | Jeyanthan Construction | 0% | 19032750 | 26884145.14 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-10 | 2026-07-10
RR/RDA/03/25/12/WP/KTR | RR/RDA/03/25/12 | Concreting Batawala Road | Kalutara | Horana | Next Engineering Services (PVT) LTD | 39% | 18670236.2 | 26342506.07 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-22 | 2026-04-21
RR/RDA/03/25/16/WP/KTR | RR/RDA/03/25/16 | Development of carpeting of 1 km from Gane Aramba Road, Bogalla Junction to Ambepitiya Pinhena | Kalutara | Kalutara | Asela Construction | 0% | 27990360 | 37805645.98 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-03 | 2026-07-03
| RR/RDA/03/25/17 | Development of 0.8 km carpeting of Newfa Mawatha | Kalutara | Kalutara | Develco Engineering (PVT) LTD | 0% | 6972603.95 | 8350944.75 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-22 | 2026-07-22
RR/RDA/03/25/18/WP/KTR | RR/RDA/03/25/18 | Development of carpeting of the section (length 800 m) from near Minerithenna temple to Jananandanarama temple | Kalutara | Kalutara | Asela Construction | 0% | 17101775 | 23076319.79 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-03 | 2026-07-03
| RR/RDA/03/25/19 | Carpeting and development of 500 meters of Moragahakanda watta Bodumaga Senasuna Viharastha Road | Kalutara | Kalutara | Develco Engineering (PVT) LTD | 55% | 8285619 | 9421190.92 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-22 | 2026-07-22
| RR/RDA/03/25/21 | Development of from Lewis Stadium to Heladiva Malshalawa | Kalutara | Kalutara | Develco Engineering (PVT) LTD | 55% | 15591781.1 | 18421245.76 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-22 | 2026-07-22
RR/RDA/06/25/44 |  | Carpeting of Muloya Main Road Section 2 | Nuwara Eliya | Hanguranketha |  | 60% | 42312390.95 | 42312390.95 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-22 | 2025-12-31 | 2026-03-15
RR/RDA/06/25/47 |  | Carpeting of the road from Gatakula to Madanwala via Diaudagama, Kottala | Nuwara Eliya | Hanguranketha |  | 38% | 28020844.83 | 28020844.83 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-12-31 | 2026-03-15
RR/RDA/05/25/23 |  | Manchanayake shed eka asala sita sampath waththa haraha Galketiyawa margaya | Matale | Nalanda |  | 60% | 28401905.12 | 28401905.12 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-12-13 | 2026-06-13
RR/RDA/05/25/28 |  | Adawala Udagama Road | Matale | Nalanda |  | 75% | 56161142.68 | 56161142.68 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-09-22 | 2026-02-22 | 2026-04-20
RR/RDA/15/25/10 |  | Concreting to Internal at MMV School | Batticaloa | Batticaloa |  | 95% | 33890314.66 | 33890314.66 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-11-15 | 2026-03-15
RR/RDA/17/25/08 |  | Concreting of Play Ground Road Mahadiulwewa Stage II | Trincomalee | Trincomalee |  | 90% | 43210842.75 | 43210842.75 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-02-02 | 2026-03-31 | 2026-03-31
RR/RDA/25/24/35 |  | Ilumba Kanda Road from Milinduthalawa Temple | Ratnapura | Embilipitiya |  | 30% | 24709638.71 | 24709638.71 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10
RR/RDA/25/24/17 |  | Pahalawaththa to Batahenkanda Road | Ratnapura | Embilipitiya |  | 10% | 112040241.38 | 112040241.38 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10
RR/RDA/25/24/19 |  | Wijeriya Iththekanda Margaya Sanwardanaya Kirima | Ratnapura | Embilipitiya |  | 35% | 72158727.69 | 72158727.69 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10
RR/RDA/25/24/20 |  | Godawela Walakada margaya Sanwardanaya Kirima (Walakada Junction to Godawela Junction) | Ratnapura | Embilipitiya |  | 15% | 126132479.8 | 126132479.8 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10
RR/RDA/08/25/05 |  | Koggalla bus stand to Sooriyawewa Road | Hambantota | Tangalle |  | 95% | 127573213.52 | 127573213.52 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-02-28
RR/RDA/09/25/07 |  | Carpeting Dabewelena Gravel Road | Hambantota | Hambantota |  | 98% | 54766473.95 | 54766473.95 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-10-18 | 2025-12-31 | 2026-03-31