## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/15/25/01/EP/BTC | RR/RDA/15/25/01 | Concreting to Vipulananthar road | Batticaloa | Batticaloa | SSK Construction | 100% | 29074090.89 | 44424075.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2026-02-08
RR/RDA/15/25/07/EP/BTC | RR/RDA/15/25/07 | Concreting to Thakwa masjith Cross Road | Batticaloa | Batticaloa | Nazeeha Hardware and Construction | 100% | 22206567.3 | 36804461.32 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-20 | 2026-02-15
RR/RDA/15/25/08 |  | Kumpila Madu Road | Batticaloa | Batticaloa |  | 100% | 32424899.67 | 32424899.67 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15