## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/02/25/05/WP/GMP | RR/RDA/02/25/05 | Improvements to 70/A Pahala Kandawala Grama Niladharee wasame suuriya mawathe athuru mawathak wana jayashantha mahathaage niwasa asalin athi para praja shaalawa dakwaa saha dakunu pasata thi wiharasthanaya dakwa kotasa | Gampaha | Negombo | Jeyanthan Construction | 100% | 16250193.4 | 21560731.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-01-29 | 2025-12-23
RR/RDA/02/25/02 |  | Development from the road in front of Kanti Teacher's house onwards to Vivekarama Temple (up to Uruwal Mawatha). | Gampaha | Gampaha |  | 100% | 10523274.77 | 10523274.77 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-15
RR/RDA/02/25/01 |  | Heendeniya Dumriya Sthanaya Dakwa Margaya | Gampaha | Nittambuwa |  | 100% | 13144147.11 | 13144147.11 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-07-09
RR/RDA/02/25/04 |  | Delpe Kadawara sita Nelumwaththa margaya arambaye sita Dewadasa mahathage niwasa dakwa Margaya | Gampaha | Negombo |  | 100% | 26006255.54 | 26006255.54 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-10
RR/RDA/02/25/07 |  | Road near Ozon Educational Institiute | Gampaha | Gampaha |  | 100% | 12058540.61 | 12058540.61 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-10-27 |  | 2025-11-05
RR/RDA/02/25/20 |  | St. Lazarus Road (Depot Road) | Gampaha | Negombo |  | 100% | 26943025.76 | 23521864.99 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 |  | 2026-03-31