## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/11/25/10/NP/MNR | RR/RDA/11/25/10 | Malikaippiddy 1st 2nd 3rd 4th Road | Mannar | Mannar | Vision Lanka Engineering (Pvt) Ltd | 100% | 22726000 | 30421965.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-26
RR/RDA/11/25/13/NP/MNR | RR/RDA/11/25/13 | Variveli Pandaraveli Road | Mannar | Mannar | Sanjeeve Construction Work | 100% | 29619833.65 | 42658765.29 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-01-30
RR/RDA/11/25/14/NP/MNR | RR/RDA/11/25/14 | Pichaivanifa Nedunkulam Scheme Internal Road 2 | Mannar | Mannar | Fahim Builders | 100% | 14944097.22 | 22523861.72 | Awarded | Tender Below 50Mn | Yes | Yes | Yes
RR/RDA/11/25/15/NP/MNR | RR/RDA/11/25/15 | Veppankulam Scheme Internal Road (Mosque) 3 | Mannar | Mannar | Sanjeeve Construction Work | 100% | 17836311.35 | 24802089.31 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-01-23
RR/RDA/11/25/19/NP/MNR | RR/RDA/11/25/19 | Chilawathurai Maiyavadi Road | Mannar | Mannar | Abdul Cader Constructions | 100% | 22899536 | 34056451.63 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-01
RR/RDA/11/25/24/NP/MNR | RR/RDA/11/25/24 | Murukan Kovil Main Road | Mannar | Mannar | Abdul Cader Constructions | 100% | 36558775 | 59821861.03 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01
RR/RDA/11/25/12 |  | Renovation of Chemmantheevu 4th Cross Street. | Mannar | Mannar |  | 100% | 25184287.62 | 25184287.62 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21 | 2025-10-31
RR/RDA/11/25/17 |  | Alakkatu Internal Road 5 | Mannar | Mannar |  | 100% | 25141870.23 | 25141870.23 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-14 | 2025-12-13 | 2025-11-04