## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/16/25/04/AKK/AMP | RR/RDA/16/25/04 | Pokunugama near Mr. Dinesh Tharaga House to Road (From Pokunugama Pre School to up to Mr. Dinesh Tharaga House) | Ampara | Ampara | Harischandra Idikirim | 100% | 6435000 | 10039653.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2025-12-10 | 2025-12-19
RR/RDA/SP/16/25/02 |  | Karana junction south pahalawela palanoya road (From near Pahalalanda post office junction to Karanagama) | Ampara | Ampara |  | 100% | 171722366.66 | 171722366.66 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-22 |  | 2025-11-15