## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/19/25/09 |  | Water front Mawatha (wennappuwa) | Puttalam | Chilaw |  | 100% | 12072583.1 | 12072583.1 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/19/25/07 |  | Development of the road from near Kalegama School to Erungwila. | Puttalam | Chilaw |  | 100% | 55009126.14 | 55009126.14 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 |  | 2025-10-31
RR/RDA/19/25/25 |  | Development of Mada Koswadiya Bogaha Road | Puttalam | Chilaw |  | 100% | 25235881.81 | 25235881.81 | Awarded | DL Stage 03 | Yes | Yes | Yes |  |  | 2025-11-05