## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/07/25/06/SP/GAL | RR/RDA/07/25/06 | Mulana Nagenahira ha Panwila Grama Niladari Wasam Sambandha wana athuru Margaya | Galle | Galle | Star Light Construction | 100% | 13805759 | 22862917.58 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-06
RR/RDA/07/25/11/SP/GAL | RR/RDA/07/25/11 | Elathota Pituwara Margaya Depasa Kanu ha Pathi Bami Yoda Carpet Kirima | Galle | Galle | Jayathissa Construction | 100% | 20801618.2 | 32148979.96 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-29
RR/RDA/07/25/12/SP/GAL | RR/RDA/07/25/12 | Galandeniya Margaya | Galle | Galle | Star Light Construction | 100% | 26433958.63 | 44471797.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/25/07 |  | Hapugala batuwanthuda Margaya Pivisume sita Roswudwatta Margaye Kelawara Dakwa Margaya (Jala Tankiya Margaya) | Galle | Galle |  | 100% | 27520890.73 | 27520890.33 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-22
RR/RDA/07/25/03 |  | Wackwella Palama asala sita aranbe handiya dakwa Margaya | Galle | Galle |  | 100% | 26781909.97 | 26781909.97 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-15
RR/RDA/07/25/04 |  | Galwehera C.P. the Silva Mawatha Carpet kirima | Galle | Galle |  | 100% | 30571235.08 | 30571235.09 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30
RR/RDA/07/25/14 |  | Moonugoda Road | Galle | Galle |  | 100% | 21211506.6 | 21211506.6 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-16
RR/RDA/07/25/22 |  | Asphalting Meepawala henegewaththa road | Galle | Galle |  | 100% | 21395564.1 | 21395564.1 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-19 | 2026-02-27 | 2026-02-28