## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/02/25/02 |  | Development from the road in front of Kanti Teacher's house onwards to Vivekarama Temple (up to Uruwal Mawatha). | Gampaha | Gampaha |  | 100% | 10523274.77 | 10523274.77 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-15
RR/RDA/02/25/07 |  | Road near Ozon Educational Institiute | Gampaha | Gampaha |  | 100% | 12058540.61 | 12058540.61 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-10-27 |  | 2025-11-05