## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/21/25/05 |  | Ketayam Kade asala sita Rampanam oya Dhakwa Margaya | Polonnaruwa | Habarana |  | 100% | 62573316.72 | 62573316.72 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-13
RR/GA/21/25/CC/13 |  | Sathutugama Nidahas mawatha sanwardhanaya kireema | Polonnaruwa | Habarana |  | 100% | 53733874.7 | 53733874.7 | Awarded | DL Stage 02 | Yes | Yes | Yes |  | 2026-01-20 | 2026-01-31
RR/GA/21/25/CC/12 |  | Girithale janapadaya pasal mawatha carpet kara ithiri kotasa wana D.G. Jayasiri mahathage niwasa asala sita Akkara 15 handiya Jhon Raja mahathage niwasa dakwa margaya | Polonnaruwa | Habarana |  | 100% | 42689736.99 | 42689736.99 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-17 |  | 2026-01-31
RR/RDA/21/25/16 |  | Diyabeduma to Jamburewela Road | Polonnaruwa | Habarana |  | 100% | 122382954.72 | 122382954.72 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-17 |  | 2026-01-31
RR/RDA/21/25/28 |  | Development of the road Sathutugama nidahas Mawatha Balance Section from the house of Mr. Lahiru Madhusanka to the house of Mr. Navaratne in the area of ​​Giritale. | Polonnaruwa | Habarana |  | 100% | 29829563.55 | 32617373.22 | Awarded | DL Stage 03 | Yes | Yes | Yes |  |  | 2026-01-31
RR/RDA/21/25/46 |  | Girithale janapadaya pasal mawatha starting Section | Polonnaruwa | Habarana |  | 100% | 22545305.56 | 22545305.56 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 |  | 2026-02-28