## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/08/25/Si |  | Sithulpauwa Rajamaha Viharaye Katharagama Para | Hambantota | Hambantota |  | 100% | 3969390.34 | 3969390.34 | Awarded | DL Stage 01 | Yes | Yes | Yes |  | 2025-08-15
RR/RDA/09/25/01 |  | Karametiya Road | Hambantota | Hambantota |  | 100% | 74446690.12 | 74446690.12 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15
RR/RDA/09/25/02 |  | Wam Iwura Janawasa Margaya | Hambantota | Hambantota |  | 100% | 37666563.49 | 37666563.49 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30 | 2025-10-25