## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/03/25/05/WP/KTR | RR/RDA/03/25/05 | From near Mr. Abeywardena's house on the Yawita Kammalgoda road block stones and development (first phase) | Kalutara | Horana | Develco Engineering (PVT) LTD | 100% | 21827299.85 | 31800339.88 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-01-29
RR/RDA/03/25/04 |  | Development of the Kotupathgoda road by asphalting | Kalutara | Horana |  | 100% | 32439574.76 | 32439574.76 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21 | 2025-11-15