## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/03/25/02/WP/KTR | RR/RDA/03/25/02 | Concreting of the first side road on the left side of Rasik Road | Kalutara | Kalutara | Develco Engineering (PVT) LTD | 100% | 7705537.2 | 11126896.75 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2025-12-29
RR/RDA/03/25/03/WP/KTR | RR/RDA/03/25/03 | Carpeting of Uswatta Lane | Kalutara | Kalutara | Ramano Engineers | 100% | 6059612.5 | 7444801.7 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2025-12-29
RR/RDA/03/25/01 |  | Asphalting Samagipura Road (LECO office to Maha ela) | Kalutara | Kalutara |  | 100% | 25713214.4 | 25713214.4 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/03/25/07 |  | Carpeting of Shekmadara Road | Kalutara | Kalutara |  | 100% | 14674228.65 | 14674228.65 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-07-14 | 2025-08-07
RR/RDA/03/25/11 |  | Jilani road in Darga Town | Kalutara | Kalutara |  | 100% | 14759196.13 | 14759196.13 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-17 | 2025-11-25
RR/RDA/03/25/20 |  | Development of Gemunu Mawatha by laying 500 meters of carpet | Kalutara | Kalutara |  | 100% | 12547527.78 | 12547527.78 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-12 | 2026-01-31