## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/04/25/15/CP/KY | RR/RDA/04/25/15 | Madolkale sita Huluganga dakwa yana athuru margaye Bandaranayakapura gam kotasata adala Margaya | Kandy | Kundasale | UGD Constructions | 100% | 12711509.59 | 20856501.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-02-28
RR/RDA/04/25/22/CP/KY | RR/RDA/04/25/22 | Rambukwella viharasthanaya asala sita Dodamgolla Rambukwella nagenhira haraha Udispaththuwa dakwa diwena Margaya | Kandy | Kundasale | The Wise Lanka Construction Company (Pvt) Ltd | 100% | 15056107 | 26802449.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-02-28
RR/RDA/04/25/23/CP/KY | RR/RDA/04/25/23 | Minuwangamuwa gammada margaye Aberathne mahathage niwasa asala sita Abesinha Banda mahathage Niwasa dakwa | Kandy | Kundasale | The Wise Lanka Construction Company (Pvt) Ltd | 100% | 27734432.55 | 49079937.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-01 | 2026-01-14 | 2026-03-31
RR/RDA/04/25/32/CP/KY | RR/RDA/04/25/32 | Pilawala Navodya pasala asala sita Nelumpathhinna pansala dakwa margaya | Kandy | Kundasale | Senerath Engineering (pvt) Ltd | 100% | 18059531.27 | 19939938.98 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-01-31
RR/RDA/04/25/43/CP/KY | RR/RDA/04/25/43 | Dodamgolla kowila asla sita hindu susana boomiya dakwa margaya | Kandy | Kundasale | The Wise Lanka Construction Company (Pvt) Ltd | 100% | 14680539.5 | 26797465.46 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-02-28
RR/RDA/04/25/42 |  | Mahanuwara Digana pradana margaye gamudawa jala tankiya asala sita Malgahamula handiya dakwa Margaya | Kandy | Kundasale |  | 100% | 21611921.71 | 21611921.71 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-07-21
RR/RDA/04/25/37 |  | Elkaduwa pare sita Japan para sanwardanaya kirima | Kandy | Kundasale |  | 100% | 48931555.87 | 48931555.87 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-07-30 | 2025-10-30 | 2026-02-15
RR/RDA/04/25/47 |  | Manikhinna Hurikaduwa Iththamaliyagoda New Temple Access Road | Kandy | Kundasale |  | 100% | 10442337.36 | 10442337.36 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-16 | 2026-01-25