## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/18/25/02/NWP/KRG | RR/RDA/18/25/02 | Road from Parakumpura to Yaya 04 | Kurunegala | Maho | Ingress Engineering | 100% | 20126522.24 | 24748740.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-29 | 2026-02-04 | 2025-12-28
RR/RDA/18/25/08/NWP/KRG | RR/RDA/18/25/08 | Paving of road from Nammuawa to Nagansole temple | Kurunegala | Maho | Omega Construction (Pvt) Ltd | 100% | 33899382 | 49176148.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-04 | 2026-03-07 | 2025-12-20
RR/RDA/18/25/05 |  | 158 Digana Grama niladari wasame 3 patumaga (vawa dakwa) (Yapahuwa) | Kurunegala | Maho |  | 100% | 11774916.28 | 11443000 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/18/25/99 |  | Rajanganaya reservoir to Parakumpura Junction (Left bank Road) | Kurunegala | Maho |  | 100% | 312810182.55 | 312810182.55 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 |  | 2026-02-28
RR/RDA/18/25/06 |  | Walaliya Piduruwellewa road to the middle of the village | Kurunegala | Maho |  | 100% | 19431074.96 | 19537451.95 | Awarded | DL Stage 02 | Yes | Yes | Yes