## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/05/25/01/CP/MTL | RR/RDA/05/25/01 | Moragahamada pasala asalin arambhawa Rajagammana gama madin Madawala adawala para dakwa pradana athuru Margaya | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 41535473.64 | 60115019.16 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-22 | 2026-05-26 | 2026-05-20
RR/RDA/05/25/02/CP/MTL | RR/RDA/05/25/02 | Lakshahena maragaya Mathalapitiya margaye sita Lakshahena Kosgolla dakwa Margaya | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 36743107.5 | 50437576.84 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-18 | 2025-12-31 | 2026-01-07
RR/RDA/05/25/04/CP/MTL | RR/RDA/05/25/04 | Aiththaliyadda sita Porcilain eka dakwa Margaya | Matale | Matale | Ajith Construction | 100% | 27015791 | 33583183.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2026-01-07 | 2025-12-31
RR/RDA/05/25/12/CP/MTL | RR/RDA/05/25/12 | A9 pare Kist biscuit factoryata meha sithuwam kanda board eka (savikara athi) Nalanda wattata yana para | Matale | Matale | Senevirathna Enterprise | 100% | 10340000 | 14006802.35 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-07 | 2026-01-05 | 2026-01-02
RR/RDA/05/25/13/CP/MTL | RR/RDA/05/25/13 | A9 pare Elik Aluvihare niwasa lagin arambha wee Hunugalwala dakwa margaya | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 19486197.5 | 27383521.12 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-08 | 2026-01-31
RR/RDA/05/25/16/CP/MTL | RR/RDA/05/25/16 | Dangan pedesa Mithragama margya Kurunegala margaye sita Mithragama | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 23856545.35 | 33031745.33 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-08 | 2025-12-31
RR/RDA/05/25/17/CP/MTL | RR/RDA/05/25/17 | Ambagastenna to gurubebila temple via Polwaththa nikawella | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 56391365.63 | 73216443.75 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-03-25 | 2026-03-20
RR/RDA/05/25/18/CP/MTL | RR/RDA/05/25/18 | Bandarapola Ulpathapitiya haraha Kiula margaya | Matale | Matale | Ajith Construction | 100% | 26720870 | 34151478.52 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2026-01-07 | 2025-12-31
RR/RDA/05/25/19/CP/MTL | RR/RDA/05/25/19 | Katudeniya bahukarya godanagilla asala Hettiyawatta dakwa margaya | Matale | Matale | Ajith Construction | 100% | 13129506.5 | 17556901.6 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-02-15
RR/RDA/05/25/20/CP/MTL | RR/RDA/05/25/20 | Harispattuwa margaya arambaka mansandiye sita Thusitha maranadara godanagilla dakwa | Matale | Matale | Ajith Construction | 100% | 15584937.5 | 21943997.74 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2026-01-07 | 2026-01-31
RR/RDA/05/25/27/CP/MTL | RR/RDA/05/25/27 | Welemulla sita Kandewaththa | Matale | Matale | Ajith Construction | 100% | 23207525 | 32539052.69 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-01-20
RR/RDA/05/25/29/CP/MTL | RR/RDA/05/25/29 | Pitawala handiye sita pitawala desata | Matale | Matale | Lahiru Construction & Consultants (PVT) Ltd | 100% | 37136372.9 | 38781690.92 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-23 | 2026-02-15
RR/RDA/05/25/03 |  | Serugolla Middle Road Kanwawala Junction to NawarathnaGoda Main Road | Matale | Matale |  | 100% | 29509544.69 | 30080524.87 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-19 | 2025-09-30
RR/RDA/05/25/15 |  | Salagama margaya Nikagolla margaye sita Boraluwa dakwa | Matale | Matale |  | 100% | 31665473.42 | 31665473.42 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-30