## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/25/24/15 |  | D03 Road Near the Yaka Poll | Ratnapura | Pelmadulla |  | 100% | 52683572.48 | 52683572.48 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/25/24/09 |  | From Koralegama to Labuwalwaththa Road (From Mr.Pushpananda House) | Ratnapura | Pelmadulla |  | 100% | 33251409.79 | 33251409.79 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-09-09 | 2025-11-15 | 2025-11-05