## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/25/24/04/SBP/RTP | RR/RDA/25/24/04 | Keenagahawila Kanuggala Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 33392908.77 | 49180179.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/25/24/05/SBP/RTP | RR/RDA/25/24/05 | From Nadurana Kosgas Junction to Bathalakotuwa Via Kiriporuwa Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 21592962.26 | 30993635.49 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/25/24/06/SBP/RTP | RR/RDA/25/24/06 | Hewainna Koshenagama Road | Ratnapura | Ratnapura | Asela Construction | 100% | 18485912.16 | 26723132.29 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/25/24/13/SBP/RTP | RR/RDA/25/24/13 | Henyaya - Mirishena South Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 10331554.6 | 13467295.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-17 | 2026-02-19
RR/RDA/25/24/14/SBP/RTP | RR/RDA/25/24/14 | Pimbura- Peelwatta Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 15010646.74 | 19335843.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-17 | 2026-02-19 | 2026-02-19
RR/RDA/25/24/16/SBP/RTP | RR/RDA/25/24/16 | Kalawana Salgaha Yata Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 34292579.12 | 50567711.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/25/24/07 |  | Godawela Wela Middle Road (Const. side walls) | Ratnapura | Ratnapura |  | 100% | 21801991.89 | 21801991.89 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/25/24/12 |  | Siyabalagahayata Junction to Blue Mountain Housing Complex Road | Ratnapura | Ratnapura |  | 100% | 23571917.19 | 23571917.19 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-09-04 | 2025-10-10
RR/RDA/25/24/11 |  | Cinema Hall Road to Dooliyangodella Pitawaththa Road | Ratnapura | Ratnapura |  | 100% | 27759052.36 | 27759052.36 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-02 | 2025-11-30 | 2025-11-15