## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/10/25/03/NP/JFN | RR/RDA/10/25/03 | Navalar Road | Jaffna | Jaffna | KBS Engineering Solution | 100% | 7919722.64 | 16240094.76 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-31 | 2026-04-01 | 2026-06-08
RR/RDA/10/25/04/NP/JFN | RR/RDA/10/25/04 | Aluminium Factory Road | Jaffna | Jaffna | Majurathas Building Contractors | 100% | 36973948 | 56580112.16 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-03 | 2026-04-04 | 2026-06-08
RR/RDA/10/25/05/NP/JFN | RR/RDA/10/25/05 | Renovation of Kokkuruniya Veethy | Jaffna | Jaffna | Majurathas Building Contractors | 100% | 22247557.75 | 34746312.4 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-06
RR/RDA/10/25/08/NP/JFN | RR/RDA/10/25/08 | Renovation of Ilanthaikulam Road | Jaffna | Jaffna | KBS Engineering Solution | 100% | 12089810.15 | 17821627.52 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13 | 2026-02-13
RR/RDA/10/25/10/NP/JFN | RR/RDA/10/25/10 | Nayanmar Road | Jaffna | Jaffna | AVP Construction (Pvt) Ltd | 100% | 17917437.01 | 27107876.22 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13 | 2026-02-13
RR/RDA/10/25/11/NP/JFN | RR/RDA/10/25/11 | Amman Road | Jaffna | Jaffna | Thaaru Construction | 100% | 14588981 | 19749993.06 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-05 | 2026-03-05
RR/RDA/10/25/13/NP/JFN | RR/RDA/10/25/13 | lnbacholai Road (Iththiyadi Muthali Kovilady - Inbacholai Road) | Jaffna | Jaffna | AVP Construction (Pvt) Ltd | 100% | 22527821.25 | 33467961.12 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-05-12 | 2026-05-12
RR/RDA/10/25/15/NP/JFN | RR/RDA/10/25/15 | Kadavaippulam Road | Jaffna | Jaffna | KBS Engineering Solution | 100% | 7712452 | 12352166.19 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13 | 2026-02-13
RR/RDA/10/25/16/NP/JFN | RR/RDA/10/25/16 | Kalai Makal Road | Jaffna | Jaffna | Jana Civil Work Contractors and Material Suppliers | 100% | 17670712.18 | 25146295.8 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-06
RR/RDA/10/25/20/NP/JFN | RR/RDA/10/25/20 | Thuvali Veethy | Jaffna | Point Pedro | Majurathas Building Contractors | 100% | 32948293.95 | 47624825.22 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13 | 2026-02-13
RR/RDA/12/25/02/NP/VVN | RR/RDA/12/25/02 | Eswarypuram housing scheme internal road (NVSTE178) | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 100% | 28833609.2 | 40810577.98 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/05/NP/VVN | RR/RDA/12/25/05 | Sinnakulam road – laxapana road | Vavuniya | Vavuniya | Arul Selvi Construction and Hardware | 100% | 16411999.99 | 21459717.36 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13 | 2026-02-13
RR/RDA/12/25/08/NP/VVN | RR/RDA/12/25/08 | Katkulam road | Vavuniya | Vavuniya | Yansika Success Group (Pvt) Ltd | 100% | 18055415.95 | 22884956.34 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-04
RR/RDA/12/25/26/NP/VVN | RR/RDA/12/25/26 | Cemetery Road | Vavuniya | Vavuniya | Ranasinghe Construction | 100% | 17011533 | 23875168.24 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/30/NP/VVN | RR/RDA/12/25/30 | Maradammaduwa Rural Road | Vavuniya | Vavuniya | Sevvel Construction & Suppliers | 100% | 25533435.95 | 33292513.97 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-03-18
RR/RDA/12/25/32/NP/VVN | RR/RDA/12/25/32 | Kalukummankaduwa to Alagalla Rural Road | Vavuniya | Vavuniya | Yansika Construction | 100% | 36671440.85 | 61020259.1 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-03-04
RR/RDA/12/25/33/NP/VVN | RR/RDA/12/25/33 | Mamaduwa Thiyawaragama Road | Vavuniya | Vavuniya | 5N Group Construction | 100% | 20811747 | 26687363.08 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-02-21
RR/RDA/12/25/36/NP/VVN | RR/RDA/12/25/36 | Mamaduwa to Dikwewa | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 100% | 18006430.2 | 25629657.32 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/37/NP/VVN | RR/RDA/12/25/37 | Parakumawatha | Vavuniya | Vavuniya | Ranasinghe Construction | 100% | 26672047.6 | 34830175.61 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-24 | 2026-01-23
RR/RDA/12/25/39/NP/VVN | RR/RDA/12/25/39 | Madukanda lake side road | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 100% | 22687590.2 | 31883174.61 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/42/NP/VVN | RR/RDA/12/25/42 | Veerapuram main road (veerapuram 2nd 3rd lane) | Vavuniya | Vavuniya | Yaso Engineering | 100% | 19745000 | 25380543.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/46/NP/VVN | RR/RDA/12/25/46 | Sinnasippikulam to neriyakulam road | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 100% | 14561522.25 | 21276360.97 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/53/NP/VVN | RR/RDA/12/25/53 | Ethawetunuwewa Temple Road | Vavuniya | Vavuniya | Shiyamala Construction | 100% | 9515000 | 12174775.32 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/55/NP/VVN | RR/RDA/12/25/55 | Mayawewa to Namalpura Road | Vavuniya | Vavuniya | Yansika Construction | 100% | 17639615.95 | 22825561.83 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/56/NP/VVN | RR/RDA/12/25/56 | From Nikawewa Post Office to Nikawewa Right Village | Vavuniya | Vavuniya | Yansika Construction | 100% | 17924713.95 | 23412051.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/57/NP/VVN | RR/RDA/12/25/57 | Nikawewa Right to Sapumalthanna | Vavuniya | Vavuniya | Yansika Construction | 100% | 11848115.95 | 15184106.87 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/58/NP/VVN | RR/RDA/12/25/58 | Preschool Road | Vavuniya | Vavuniya | 5N Group Construction | 100% | 21518222 | 28313232.5 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-10 | 2026-02-08
RR/RDA/12/25/59/NP/VVN | RR/RDA/12/25/59 | Kalyanipura 2nd lane | Vavuniya | Vavuniya | 5N Group Construction | 100% | 28184992 | 37048858.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-12
RR/RDA/11/25/10/NP/MNR | RR/RDA/11/25/10 | Malikaippiddy 1st 2nd 3rd 4th Road | Mannar | Mannar | Vision Lanka Engineering (Pvt) Ltd | 100% | 22726000 | 30421965.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-26
RR/RDA/11/25/13/NP/MNR | RR/RDA/11/25/13 | Variveli Pandaraveli Road | Mannar | Mannar | Sanjeeve Construction Work | 100% | 29619833.65 | 42658765.29 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-01-30
RR/RDA/11/25/14/NP/MNR | RR/RDA/11/25/14 | Pichaivanifa Nedunkulam Scheme Internal Road 2 | Mannar | Mannar | Fahim Builders | 100% | 14944097.22 | 22523861.72 | Awarded | Tender Below 50Mn | Yes | Yes | Yes
RR/RDA/11/25/15/NP/MNR | RR/RDA/11/25/15 | Veppankulam Scheme Internal Road (Mosque) 3 | Mannar | Mannar | Sanjeeve Construction Work | 100% | 17836311.35 | 24802089.31 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-01-23
RR/RDA/11/25/19/NP/MNR | RR/RDA/11/25/19 | Chilawathurai Maiyavadi Road | Mannar | Mannar | Abdul Cader Constructions | 100% | 22899536 | 34056451.63 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-01
RR/RDA/11/25/24/NP/MNR | RR/RDA/11/25/24 | Murukan Kovil Main Road | Mannar | Mannar | Abdul Cader Constructions | 100% | 36558775 | 59821861.03 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01
RR/RDA/10/25/21 |  | 3rd Cross Street | Jaffna | Point Pedro |  | 100% | 11072958.55 | 11072958.55 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21 | 2025-10-30
RR/RDA/10/25/17 |  | College Road | Jaffna | Jaffna |  | 100% | 35288918.91 | 35288918.91 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/12/25/44 |  | Menicfarm school road (0.5km) (NVVPE97) | Vavuniya | Vavuniya |  | 100% | 11100861.98 | 11100861.98 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/13/25/09 |  | Aninchiyankulam 2nd Lane MUTE095 | Mullaitivu | Mullaitivu |  | 100% | 46445947.77 | 46445947.77 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-11-21 | 2025-09-21
RR/RDA/11/25/12 |  | Renovation of Chemmantheevu 4th Cross Street. | Mannar | Mannar |  | 100% | 25184287.62 | 25184287.62 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21 | 2025-10-31
RR/RDA/10/25/12 |  | Anaikoddai - Kakaithivu Road | Jaffna | Jaffna |  | 100% | 34361480.4 | 34361480.4 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-11 | 2025-11-10
RR/RDA/10/25/26 |  | VC Road No 15 | Jaffna | Point Pedro |  | 100% | 23825730.98 | 23825730.98 | Awarded | DL Stage 02 | Yes | Yes | Yes |  |  | 2026-03-31
RR/RDA/12/25/06 |  | Paalavinayagar road | Vavuniya | Vavuniya |  | 100% | 17373382.99 | 18688450.91 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-14 | 2025-11-13 | 2026-02-28
RR/RDA/13/25/04 |  | Suthanthirapuram Main Road Package 1 | Mullaitivu | Mullaitivu |  | 100% | 110821121.4 | 110821121.4 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-13 | 2025-11-12 | 2025-11-30
RR/RDA/11/25/17 |  | Alakkatu Internal Road 5 | Mannar | Mannar |  | 100% | 25141870.23 | 25141870.23 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-14 | 2025-12-13 | 2025-11-04
RR/RDA/14/25/05 |  | Kanakapuram school behind road | Kilinochchi | Kilinochchi |  | 100% | 43582937.83 | 43582937.83 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-10-16 |  | 2026-03-31
RR/RDA/13/25/05 |  | Suthanthirapuram Main Road Package 2 | Mullaitivu | Mullaitivu |  | 100% | 63852534.37 | 63852534.37 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-30 | 2026-02-06
RR/RDA/12/25/11 |  | Madeenanagar road | Vavuniya | Vavuniya |  | 100% | 21394474.49 | 21394474.49 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-10-16 | 2025-11-01 | 2025-11-01
RR/RDA/13/25/02 |  | Kokkilai Estuary fishing village Road | Mullaitivu | Mullaitivu |  | 100% | 26445698.08 | 26445698.08 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-03-31
RR/RDA/10/25/23 |  | Oorany Kudiyetta thidda Veethy | Jaffna | Point Pedro |  | 100% | 12148965.86 | 12148965.86 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-03-31