## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/25/24/04/SBP/RTP | RR/RDA/25/24/04 | Keenagahawila Kanuggala Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 33392908.77 | 49180179.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/25/24/05/SBP/RTP | RR/RDA/25/24/05 | From Nadurana Kosgas Junction to Bathalakotuwa Via Kiriporuwa Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 21592962.26 | 30993635.49 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/25/24/06/SBP/RTP | RR/RDA/25/24/06 | Hewainna Koshenagama Road | Ratnapura | Ratnapura | Asela Construction | 100% | 18485912.16 | 26723132.29 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/25/24/13/SBP/RTP | RR/RDA/25/24/13 | Henyaya - Mirishena South Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 10331554.6 | 13467295.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-17 | 2026-02-19
RR/RDA/25/24/14/SBP/RTP | RR/RDA/25/24/14 | Pimbura- Peelwatta Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 15010646.74 | 19335843.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-17 | 2026-02-19 | 2026-02-19
RR/RDA/25/24/16/SBP/RTP | RR/RDA/25/24/16 | Kalawana Salgaha Yata Road | Ratnapura | Ratnapura | SSP Engineering | 100% | 34292579.12 | 50567711.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/25/25/05/SBP/KGL | RR/RDA/25/25/05 | Siyabalangamuwa Kudumbuwa Road | Kegalle | Kegalle | Shanho Engineering | 100% | 39262197.06 | 46027479.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-04
RR/RDA/25/25/06/SBP/KGL | RR/RDA/25/25/06 | From Dombemada Post Office to Sillugala Via Wedollamada well | Kegalle | Kegalle | Shanho Engineering | 100% | 37416631.86 | 45066393.95 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-04
RR/RDA/25/25/09/01/SBP/KGL | RR/RDA/25/25/09/01 | The first phase of the Matiyagane-Berawandare road from Mas Potha via Haliyagoda | Kegalle | Kegalle | Samindra construction | 100% | 26656967.36 | 28713235.52 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-04
RR/RDA/25/25/10/SBP/KGL | RR/RDA/25/25/10 | Elipangamuwa School Road through Pananawaththa | Kegalle | Kegalle | DHP Construction | 100% | 23988665.8 | 33397400.45 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-03 | 2026-02-01
RR/RDA/25/25/31/SBP/KGL | RR/RDA/25/25/31 | Developing the section connecting the road from the old office in Yatawala to the road in Beraliyahinna | Kegalle | Ruwanwella | DHP Construction | 100% | 13369909.3 | 14520809.96 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-04
RR/RDA/25/25/32/SBP/KGL | RR/RDA/25/25/32 | Concreting the unconcreted areas of the Hingurana road | Kegalle | Ruwanwella | DHP Construction | 100% | 15740043.19 | 17242742.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-04
RR/RDA/25/25/33/SBP/KGL | RR/RDA/25/25/33 | Rehabilitation of Kahatapanawa Kajugahamula road | Kegalle | Ruwanwella | Jayabima Engineering | 100% | 12423785 | 16993706.54 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-20 | 2026-02-18
RR/RDA/25/24/07 |  | Godawela Wela Middle Road (Const. side walls) | Ratnapura | Ratnapura |  | 100% | 21801991.89 | 21801991.89 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/25/24/15 |  | D03 Road Near the Yaka Poll | Ratnapura | Pelmadulla |  | 100% | 52683572.48 | 52683572.48 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/25/24/08 |  | From Mr.Ranjth's House to Mr.Premasiri's House in Maduwanwela Janapadaya 2nd Lane Road | Ratnapura | Embilipitiya |  | 100% | 39030233.29 | 39030233.29 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/25/25/16 |  | Ma dola Jansalu Mawatha Rathnapuara Colombo Road to Welangalla Maha ela Bridge | Kegalle | Ruwanwella |  | 100% | 40604043.84 | 37225336.73 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-25
RR/RDA/25/25/17 |  | Na gahamula Junction to 28 Janapadaya Road | Kegalle | Kegalle |  | 100% | 30370502.56 | 30370502.56 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/25/24/12 |  | Siyabalagahayata Junction to Blue Mountain Housing Complex Road | Ratnapura | Ratnapura |  | 100% | 23571917.19 | 23571917.19 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-09-04 | 2025-10-10
RR/RDA/25/24/09 |  | From Koralegama to Labuwalwaththa Road (From Mr.Pushpananda House) | Ratnapura | Pelmadulla |  | 100% | 33251409.79 | 33251409.79 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-09-09 | 2025-11-15 | 2025-11-05
RR/RDA/25/25/18 |  | Concreting Beragala Army Camp to Beragala 3way Junction VIA Niyadagala | Kegalle | Kegalle |  | 100% | 34687905.11 | 34687905.11 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-26 | 2025-10-31 | 2025-10-25
RR/RDA/25/25/21 |  | Kalupahanawaththa Road | Kegalle | Ruwanwella |  | 100% | 28324647.09 | 28324647.09 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-07 | 2025-11-30 | 2025-11-15
RR/RDA/25/24/11 |  | Cinema Hall Road to Dooliyangodella Pitawaththa Road | Ratnapura | Ratnapura |  | 100% | 27759052.36 | 27759052.36 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-02 | 2025-11-30 | 2025-11-15
RR/RDA/25/25/30 |  | Developing the dilapidated section of the lower part of the Pallebage road to the Watte junction | Kegalle | Ruwanwella |  | 100% | 6992158.2 | 6992158.2 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-18 | 2025-10-10